## 📊 Dashboard
🚂 KlimaChallenge — TravelApp ¦ Project Management & Development Diary
Session 12 Complete · 2026-03-16 · React Native / Expo SDK 54 · Supabase · TypeScript
KEY METRICS
Sessions Completed |  | Features Shipped |  | Backlog Remaining |  | Tech Debt Items |  | Pre-Prod Blockers
12 |  | 35 |  | 5 |  | 0 |  | 4
prev: 12 |  | prev: 35 |  | prev: 10 |  | prev: 9 |  | prev: 4
MILESTONE PROGRESS
ID | Milestone |  | Target |  | Status |  | Completion |  | Blocker
M1 | Core MVP | 2026-03-14 | ✅ Complete |  | 100% |  | —
M2 | Auth & Onboarding | 2026-03-15 | ✅ Complete |  | 100% |  | —
M3 | Full Trip Lifecycle | 2026-03-15 | ✅ Complete |  | 100% |  | —
M4 | UX Polish | 2026-03-15 | ✅ Complete |  | 100% |  | —
M5 | Gamification 2.0 | 2026-03-15 | ✅ Complete |  | 100% |  | —
M6 | Stats & Insights | 2026-03-16 | ✅ Complete |  | 100% |  | —
M7 | Production Ready | 2026-04-12 | ⬜ Planned |  | 0% |  | Images, email confirm, App Store assets
SESSION VELOCITY (features shipped per session)
Session | Date | Key Focus | Features | Category Mix | Cumulative | Bar
S1 | Mar 13 | Pre-session bug fix + SDK upgrade | — | Bug Fix / Infra | — | ░░░░░░░░░░
S2 | Mar 14 | Trip CRUD, FinancialOverview, accent bars, seed data | 4 | Infra / Core | 4 | ████░░░░░░
S3 | Mar 14 | Favorites RNGH, XP/level system, UserLevelCard | 3 | UX / Gamification | 7 | ███░░░░░░░
S4 | Mar 15 | TripDetailModal, XP seed fix, logout, UX overhaul | 4 | Bug Fix / UX | 11 | ████░░░░░░
S5 | Mar 15 | Supabase auth, dark Login+Register, Onboarding, Splash | 3 | Auth / Onboarding | 14 | ███░░░░░░░
S6 | Mar 15 | Trip editing, XPToast, LevelUpOverlay, profile, settings | 9 | Features / UX | 23 | ██████████
S7 | Mar 15 | TripRouteFields, price autofill, suggestions, swap, estimator | 5 | Refactor / UX | 28 | ██████░░░░
S8 | Mar 15 | ÖBB fix, QuickAdd dark theme, description autofill, PM Excel | 7 | Bug Fix / UI | 35 | ████████░░
S9 | Mar 15 | Quest system, achievements, Quests screen, Main Quest | 8 | Gamification | 43 | █████████░
S10 | Mar 16 | Stats & Insights screen, entry points | 3 | Stats | 46 | ███░░░░░░░
S11 | Mar 16 | Tech debt sprint: 9 items cleared | — | Tech Debt | — | ░░░░░░░░░░
S12 | Mar 16 | KlimaTicket presets, Delete All Trips, 4 bug fixes | 2 | Feature / Bug Fix | 48 | ██░░░░░░░░

## 📓 Session Diary
📓 KlimaChallenge — Session Diary
Chronological record of every development session — decisions made, problems encountered, alternatives rejected, and lessons learned. Primary source for methodology chapters.
Session | Date | Scope / Theme | What was built — deliverables & files | Why — motivation & design rationale | Problems encountered | Alternatives rejected | Decisions & gotchas for future reference | Features # | Effort est. | Thesis tag
Pre-S | 2026-03-13 | Bug triage + SDK 52→54 upgrade | Fixed 5 pre-existing bugs: calculateLevel crash on 0 XP, broken transport type matching in XP formula, trip detail screen showing hardcoded Paris/Tokyo/Bali data, duplicated service code in user.tsx, date picker showing future dates. Upgraded Expo 52→54 (React 18→19, RN 0.76→0.81, expo-router v4→v6). Files: levelSystem.ts, trip/[id].tsx, user.tsx, QuickAddTripModal.tsx, FinancialOverview.tsx, package.json, app.config.ts, metro.config.js, _layout.tsx | App was non-functional before feature work could begin. SDK upgrade needed to access Reanimated v4 and expo-router v6 typed routes. Chose to do full triage before any new features to establish a clean baseline. | Math.log(0) = -Infinity caused level display to break. Supabase 'ws' package requires Node.js 'stream' built-in, unavailable in React Native — shimmed to empty module in metro.config.js. react-native-worklets required as explicit peer dep for Reanimated v4. | Could have deferred SDK upgrade to a later session, but expo-router v6 typed routes were needed for auth flow architecture planned in S5. | URL polyfill must be first import in _layout.tsx. IconSymbol TextStyle vs ViewStyle mismatch — RN 0.81 tightened type. Asset paths must be ./assets/images/ not ./assets/. | — | ~4h | System Setup / Bug Analysis
S1 | 2026-03-14 | Core MVP — trip data layer | Trip CRUD via AsyncStorage (key: @travelapp_trips). FinancialOverview collapsible savings card with SVG donut. 10 dummy seed trips for testing. Transport accent bars on trip cards. Files: services/tripStorage.ts, app/(tabs)/user.tsx, FinancialOverview.tsx | Established the foundational data loop before any UI polish: add trip → save → reload → display. FinancialOverview built immediately because it is the core value proposition (break-even tracking), not a decorative feature. | klimaTicketCost was hardcoded as €1297.80 inside FinancialOverview — discovered when prop passed as €1090 had no effect. Resolved in S6. | Considered SQLite for persistence, rejected in favour of AsyncStorage for simplicity at this stage. Supabase sync deferred to post-MVP. | AsyncStorage key @travelapp_trips chosen (not @trips) — this distinction caused the Delete All Trips bug in S12. Never use removeItem on wrong key. | 4 | ~3h | System Architecture / Data Layer
S2 | 2026-03-14 | Gamification core — XP, levels, Favorites | XP/level system: getXPForTrip (base 10 + distance capped 50km × transport multiplier), calculateLevel (exponential curve), getLevelTitle. UserLevelCard with animated XP progress bar. Favorites hold-to-add (RNGH LongPress 1000ms, Reanimated fill animation). Show all / Show less toggle on trip list. Files: utils/levelSystem.ts, UserLevelCard.tsx, user.tsx, user_styles.tsx | XP formula was designed to reward frequency over distance (base 10 XP even for short trips) and to incentivise less car-like modes (Tram 1.4× multiplier highest because trams are most climate-positive per km). Cap at 50km prevents one long journey from dominating the level curve. | Favorites hold gesture failed with 5 successive approaches: TouchableOpacity onPressIn — scroll delay; Pressable onPressIn — intercepted by ScrollView native gesture; onTouchStart — same; PanResponder — JS-layer only, loses to native scroll; scrollEnabled toggle — race condition on release. | TouchableOpacity, Pressable, onTouchStart, PanResponder, scrollEnabled toggle all tried and failed. RNGH operates at native gesture layer and correctly negotiates with ScrollView via GestureHandlerRootView. | GestureHandlerRootView must wrap the entire app in _layout.tsx, not just the screen. Any hold/drag interaction inside a ScrollView must use RNGH. | 3 | ~4h | Gamification Design / Gesture Interaction
S3 | 2026-03-15 | Trip lifecycle — detail, delete, XP seeding | TripDetailModal: tap trip to view full details, delete with confirm overlay (not system dialog), XP subtracted on delete. XP seeding: seed from all trips if stored value is missing or 'NaN'. Logout: red-bordered button, supabase.auth.signOut(), route to /onboarding. User page: paddingTop 52 safe-area, loading spinner, section icons, Recent Trips show-all toggle. Files: TripDetailModal.tsx, user.tsx, tripStorage.ts, register.tsx | Delete confirmation as an in-app overlay (not OS dialog) keeps the visual language consistent with the dark Palette theme. XP seeding fix was critical — users upgrading from a version with no XP storage would see level 0 despite having many trips logged. | SF Symbols (IconSymbol) do not render inside React Native Modal on iOS — icons were invisible. Required switching to MaterialIcons throughout all modal and overlay contexts. | Considered using system confirm dialog for delete — rejected because it breaks visual consistency and cannot be styled to the dark theme. | RULE: Always use MaterialIcons (not IconSymbol) inside any Modal or overlay component. SF Symbols are unreliable in Modal on iOS. | 4 | ~3h | UX Design Decisions / Platform Limitations
S4 | 2026-03-15 | Auth & First Run Experience | Real Supabase auth: signInWithPassword, signUp with name metadata. lib/supabase.ts singleton with AsyncStorage session persistence. Dark Login screen (ImageBackground + LinearGradient, Austrian map). Dark Register screen matching login design. 3-slide Onboarding FlatList pager with tappable dots. Animated splash: Reanimated scale+fade 2s, session check before routing. Files: login.tsx, register.tsx, onboarding.tsx, index.tsx, supabase.ts, LoginForm.tsx, RegisterForm.tsx | Login moved outside tab group (app/login.tsx not (tabs)/index.tsx) because (1) login is pre-auth content and should not be a tab, and (2) a root app/index.tsx splash would conflict with (tabs)/index.tsx — both resolve to '/'. router.replace() used for onboarding navigation so back button cannot return to onboarding slides from login. | Routing conflict: original (tabs)/index.tsx for login + new app/index.tsx for splash both resolve to '/' in expo-router v6. Required full FRE architecture decision. | Option A: rename (tabs)/index.tsx to home.tsx. Option B: handle FRE in _layout.tsx. Option C (chosen): move login entirely outside tabs. C chosen as most architecturally correct — tab group = authenticated only. | Email confirmation disabled in Supabase dashboard for dev convenience. MUST re-enable before production. Supabase session check via supabase.auth.getSession() in splash, not AsyncStorage flag. | 3 | ~5h | Auth Architecture / FRE Design
S5 | 2026-03-15 | Trip editing, XP feedback animations, profile | Trip editing in TripDetailModal: mode:'view'¦'edit', pre-filled form, XP delta on save (new XP − old XP, floored at 0). XPToast: floating '+N XP' badge, spring+float, 1.2s. LevelUpOverlay: full-screen, spring-in card, auto-dismiss 2.8s. Empty state: icon + CTA when no trips. KlimaTicket cost setting: dropdown presets persisted in AsyncStorage. User profile screen: avatar (initials), name input, KlimaTicket picker. Files: TripDetailModal.tsx, user.tsx, XPToast.tsx, LevelUpOverlay.tsx, profile.tsx, levelSystem.ts | XP delta on edit ensures XP always reflects actual logged data — without it, editing a trip to add more distance would not award the extra XP. KlimaTicket cost as a user setting (not hardcoded) was the fix for the silent bug where €1090 prop was ignored in favour of hardcoded €1297.80. | 9 features in one session — highest-density session. No major technical problems; complexity was in XP delta logic (must never go below 0 even if new trip XP < old trip XP). | Considered a separate edit screen (not modal) — rejected to keep the trip detail interaction self-contained. | levelSystem.ts getLevelTitle() must be a shared export (not inline in UserLevelCard) because LevelUpOverlay also needs it. | 9 | ~6h | Gamification Loop Design / Animation UX
S6 | 2026-03-15 | Shared components — TripRouteFields, autofill, ÖBB | TripRouteFields shared component: origin, destination, cost, distance, transport picker — used by both QuickAdd and TripDetailModal edit mode. Price autofill: ROUTE_PRICES (specific city pairs) + TRANSPORT_FLAT_PRICES (per-type fallback). Recent places suggestions dropdown (memoized). Swap origin/destination button. Distance estimator (haversine × 1.25). Files: TripRouteFields.tsx, oebbApi.ts, QuickAddTripModal.tsx, TripDetailModal.tsx | Before this session, QuickAdd and TripDetailModal had separate copies of the route input logic. Extracting TripRouteFields eliminated significant duplication and ensured autofill behaviour was identical in both flows. Price autofill from static tables was chosen over live API pricing because the HAFAS proxy returns no ticket prices. | Price autofill mount guard: useEffect without a guard fired on modal open, overwriting user-entered cost. Fixed with useRef(false) that skips the initial render. | Live pricing via ÖBB Scotty API or VAO researched but not evaluated in depth — static ROUTE_PRICES table chosen as pragmatic interim. | useRef(false) mount guard pattern for any useEffect that should skip the initial render. haversine × 1.25 detour factor for distance estimation. | 5 | ~5h | Component Architecture / API Integration
S7 | 2026-03-15 | ÖBB integration polish, QuickAdd dark theme, PM setup | ÖBB distance fix: summariseJourney haversine fallback when API returns 0m. QuickAdd fully converted to dark theme. Connection description autofill: 'Origin → Dest · HH:MM · TrainName'. Transport type defaults to empty (forces explicit selection; autofills from connection). QuickAdd layout improvements: field order, labels, spacing. 400ms debounce on ÖBB station search via searchDebounceRef. KlimaChallenge_PM.xlsx created (this file). pm_updater.py helper script. Files: oebbApi.ts, TripRouteFields.tsx, QuickAddTripModal.tsx, PM files | ÖBB distance bug caused all connection-sourced trips to earn 0 XP — trips logged via the ÖBB search were silently penalised versus manually entered trips. Debounce added because each keystroke was firing a network request, causing lag and potential rate limiting. | HAFAS proxy returns connections as {journeys, fromStation, toStation} but journey distance field is often 0 — required haversine fallback on station lat/lng coordinates. | ÖBB Scotty API and VAO API both explored as alternatives to macistry proxy — neither pursued yet due to auth complexity. | 400ms debounce (not 300ms) chosen to feel slightly more 'settled' on mobile keyboards. PM Excel created to support thesis documentation. | 7 | ~5h | API Integration / Development Process
S8 | 2026-03-15 | Quest system, achievements, Main Quest | Quest system: daily pool (8), weekly pool (8), milestone pool (9). Random rotation via pickRandomQuests; stored in AsyncStorage by date/week key. getClaimKey, timeUntilMidnight, daysUntilMonday helpers. Achievement system: 19 achievements × 5 categories; computeStreak, computeSavedVsCar. Quests & Achievements screen: segmented control, QuestCard, AchievementCard, XP claim with XPToast+LevelUpOverlay. MainQuestFeaturedCard (red border, €X/€Y progress, CLAIM 2000 XP). MainQuestOverlay (6 floating Reanimated stars, spring-in card, one-time flag). Files: questSystem.ts, achievementSystem.ts, quests.tsx (new), MainQuestOverlay.tsx (new), user.tsx, UserLevelCard.tsx, profile.tsx | Quest rotation uses date/week as AsyncStorage key so the selection is stable within a period (same quests all day) but randomly changes at midnight/Monday — prevents gaming the system by opening the app multiple times. Main Quest (break-even detection) is the app's emotional climax — the MainQuestOverlay is the payoff for months of trip logging. | checkMainQuest() was initially called without await — errors silently swallowed, celebration could miss-fire. Fixed in S11 with explicit await. | Considered a fixed quest set (no rotation) — rejected as it would give users nothing new to do after the first week. | 2000 XP for Main Quest (vs 50-200 for regular quests) marks it as categorically different. One-time @mainQuestCelebrated flag is critical — overlay must never fire twice. | 8 | ~6h | Gamification Theory / Motivation Design
S9 | 2026-03-15 | Quests & Achievements screen (continued from S8) | Note: the PM Excel originally skipped S9 in the session log — this entry corrects that. S9 delivered the Quests & Achievements screen UI completion and the main quest featured card integration. Considered part of the S8 gamification sprint but tracked separately in the feature velocity data. | See S8 rationale. | See S8 problems. | — | Deep-link pattern: /quests?tab=achievements for profile → achievements. | — | — | Gamification Theory
S10 | 2026-03-16 | Stats & Insights screen | app/stats.tsx: 4 stat cards (trips, distance, CO₂ saved at 0.16 kg/km, avg cost/trip). CO₂ long-press tooltip explaining methodology. KlimaTicket progress bar. WeeklyBarChart: custom View-based, 8 ISO weeks. Transport Mix: horizontal proportional bars, colour-coded. Top Routes: ranked list, top 5 by trip count. Entry points: FinancialOverview donut (onStatsPress prop) + profile button. Files: app/stats.tsx (new), FinancialOverview.tsx, profile.tsx | CO₂ factor of 0.16 kg/km derived from car average 0.21 minus public transport 0.05. Displayed as 'saved vs driving' to make it legible without requiring users to understand absolute emissions. Custom chart instead of library chosen after react-native-gifted-charts caused a Metro bundler resolution bug. | react-native-gifted-charts: Metro could not resolve one of its internal dependencies after install — no clear fix found after investigation. Custom View-based bars implemented instead in ~1h. | react-native-gifted-charts tried first. Victory Native also considered but same risk of Metro issues. Custom Views chosen as zero-dependency solution that is fully controllable. | WeeklyBarChart uses ISO week numbers as keys — important for correct Monday-start week boundaries. CO₂ stat has long-press tooltip to avoid cluttering the card with methodology text. | 3 | ~4h | Data Visualisation / Sustainability Metrics
S11 | 2026-03-16 | Tech debt clearance sprint | 9 debt items cleared: useMemo([trips]) for computeFavorites and recentPlaces. constants/transport.ts: TRANSPORT_COLOR + transportIcon() as single source. await added to checkMainQuest() in handleFavoritePress + handleQuickAddSubmit. getTripById() dead code removed from tripStorage.ts. Light theme removed from TripRouteFields. screenStyles merged into user_styles.tsx. typeIcon() hoisted to constants/transport.ts as transportIcon(). eslint-disable comment added to TripRouteFields useEffect mount guard. 400ms debounce on ÖBB search (searchDebounceRef). Project memory files added to git repo at .claude/memory/. Files: constants/transport.ts (new), user.tsx, stats.tsx, TripRouteFields.tsx, QuickAddTripModal.tsx, user_styles.tsx, tripStorage.ts, .claude/memory/ | Dedicated debt sprint before any new features — technical debt accumulates fastest in high-velocity feature sprints (S5–S9 shipped 35 features in 4 days). Memory files added to git so project context is portable across machines. | No significant technical problems — this was planned remediation work. | Could have cleared debt incrementally — chosen to batch for efficiency. | Transport constants centralised: user.tsx and stats.tsx had independent TRANSPORT_ACCENT / TRANSPORT_COLOR maps that could diverge. Single source of truth in constants/transport.ts prevents this. | — | ~3h | Software Quality / Refactoring Methodology
S12 | 2026-03-16 | KlimaTicket presets overhaul + Delete All Trips | KlimaTicket presets: TICKET_GROUPS with 6 nationwide + 20 regional variants, all real 2026 Austrian prices. Grouped dropdown with section headers. Delete All Trips with slide-to-confirm (SlideToDelete): RNGH Gesture.Pan().runOnJS(true), absolute-positioned overlay (NOT RN Modal). saveTrips([]) to clear. useFocusEffect reloads trips+XP on screen focus. Bug fixes: typeIcon() crash in stats.tsx, Expo Router route warning for user_styles.tsx (renamed to _user_styles.tsx), RNGH in Modal on iOS. Files: profile.tsx, stats.tsx, user.tsx, _user_styles.tsx (renamed) | Previous KlimaTicket presets were placeholders. Real 2026 prices needed for accurate break-even calculations — this is the app's core value proposition. Slide-to-confirm for Delete All Trips chosen over a simple button because the action is irreversible and warrants a non-trivial confirmation gesture. | 3 compounding bugs in Delete All Trips: (1) RNGH gestures dead inside RN Modal on iOS — fixed by using absolute View overlay. (2) runOnJS broken on web — fixed with .runOnJS(true) + setTimeout wrapper. (3) Wrong key: removeItem(@trips) would not clear @travelapp_trips AND would cause initialTrips fallback — fixed by calling saveTrips([]). | Simple confirmation button considered for Delete All Trips. Rejected because the irreversibility justifies a higher-friction gesture. | CRITICAL: Delete All Trips must call saveTrips([]) not removeItem. RNGH Pan gestures must use absolute View overlay, not RN Modal. Expo Router ignores files prefixed with _ in app/ directory. | 2 | ~4h | UX Patterns / Platform Bug Analysis

## 📋 Backlog
📋 KlimaChallenge — Backlog
Priority-ordered work queue — open items first, completed archive below. Updated after every session.
OPEN — Work Queue (priority order)
# | Category | Task | Description | Priority | Effort | Status | Target | Notes
36 | Bug Fix | Delete All — reset quests/achievements | handleDeleteAllTrips clears trips+XP but NOT @claimedQuests, @claimedAchievements, @dailyQuestSelection, @weeklyQuestSelection. Stale claimed state persists after reset. | 🔴 Critical | XS (30m) | ⬜ Todo | S13 | Add AsyncStorage.multiRemove for all 4 keys in handleDeleteAllTrips in profile.tsx
37 | Bug Fix | Remove initialTrips demo fallback | loadTrips() returns 10 hardcoded dummy trips when @travelapp_trips key is absent. New users see fake data on first launch. | 🔴 Critical | XS (15m) | ⬜ Todo | S13 | Change fallback from `return initialTrips` to `return []` in tripStorage.ts — single line fix
38 | UX | Profile dropdown — close on outside tap | KlimaTicket dropdown in profile stays open when tapping outside. Should close on any outside touch. | 🟡 Medium | XS (30m) | ⬜ Todo | Any | Wrap screen in TouchableWithoutFeedback or use onStartShouldSetResponder pattern
39 | Feature | Cloud sync for trips (Supabase) | Trips stored AsyncStorage-only — new device login starts from scratch. No cross-device continuity. | 🟠 High | L (1-2d) | ⬜ Todo | Any | Requires Supabase trips table schema, upsert on save, fetch on login, conflict resolution
40 | Feature | Trip export / CSV download | Allow users to export all trips as CSV. Useful for tax/Jobticket employer reimbursement. | 🔵 Low | S (2-4h) | ⬜ Todo | Any | Use expo-sharing + expo-file-system to write and share CSV
— | Research | Pricing API investigation | macistry HAFAS proxy returns no ticket prices. Candidates: ÖBB Scotty API, VAO, scraping ÖBB.at | 🟡 Medium | M (4-6h) | ⬜ Todo | Any | Needed for accurate cost autofill. Static ROUTE_PRICES table is interim solution
— | Enhancement | More prefetched route prices | Add Graz, Salzburg, Innsbruck, Linz routes to ROUTE_PRICES in TripRouteFields.tsx. Currently only Villach routes. | 🔵 Low | XS (1h) | ⬜ Todo | Any | Quick win for Austria-wide usability
PRE-PRODUCTION CHECKLIST
# | Category | Task | Description | Priority | Effort | Status | Target | Notes
PP1 | Pre-Prod | Re-enable email confirmation | Supabase email confirmation currently disabled for dev. BLOCKER for production. | 🔴 Critical | XS (5m) | ⬜ Todo | Pre-launch | Toggle in Supabase project dashboard — Authentication → Email
PP2 | Pre-Prod | Add onboarding images | onboard1.png, onboard2.png, loginbg.png missing from assets/images/. Bundler fails without them. | 🟡 Medium | S (design) | ⬜ Todo | Pre-launch | Slide 1: ROI annotated map. Slide 2: full KlimaTicket coverage map. Login bg: plain Austrian map
PP3 | Pre-Prod | App Store assets & metadata | App icon, splash, name, description, screenshots required for iOS/Android submission. | 🟡 Medium | M (1d) | ⬜ Todo | Pre-launch | EAS build + submission. Consider ASO (App Store Optimisation) for keywords
PP4 | Pre-Prod | Final regression + EAS build | Full device test on both iOS and Android before submission. | 🟡 Medium | S (2-4h) | ⬜ Todo | Pre-launch | Test: auth flow, trip CRUD, quest rotation, delete all trips, KlimaTicket cost impact
COMPLETED — Archive (read-only reference)
# | Category | Task | Description | Priority | Effort | Status | Target | Notes
1 | Bug Fix | ÖBB Distance Fix | summariseJourney() returns no distance → 0 XP trips. haversine×1.25 fallback. | 🔴 Critical | S | ✅ Done | S7 | Completed S7
2 | Feature | Quests / Tasks Page | Daily/weekly/milestone quest pools, rotation, XP claim. | 🟠 High | L | ✅ Done | S8 | Completed S8
3 | Feature | Achievements / Badges | 19 achievements × 5 categories, AchievementCard, computeStreak. | 🟠 High | M | ✅ Done | S8 | Completed S8
4 | Feature | Stats & Visualisations | app/stats.tsx — 4 stat cards, weekly bar chart, transport mix, top routes. | 🟠 High | L | ✅ Done | S10 | Completed S10
5 | Feature | CO2 Savings Display | CO2 saved stat card (0.16 kg/km); long-press tooltip. | 🟡 Medium | S | ✅ Done | S10 | Completed S10
6 | Feature | Trip Statistics Summary | Transport Mix + Top Routes + avg cost/trip. | 🟡 Medium | S | ✅ Done | S10 | Completed S10
9 | Tech Debt | Memoize computeFavorites | useMemo([trips]) in user.tsx | 🔵 Low | XS | ✅ Done | S11 | Completed S11
10 | Tech Debt | Centralise transport constants | constants/transport.ts — TRANSPORT_COLOR + transportIcon() | 🔵 Low | XS | ✅ Done | S11 | Completed S11
11 | Tech Debt | Normalise trip.date on load | loadTrips() coerces date: new Date(trip.date). Closed S9 audit. | 🟡 Medium | XS | ✅ Done | S7 | Already resolved
12 | Tech Debt | Debounce ÖBB search | 400ms debounce via searchDebounceRef in QuickAddTripModal | 🔵 Low | XS | ✅ Done | S11 | Completed S11
16 | Bug Fix | Price autofill mount fix | useRef(false) guard in TripRouteFields prevents autofill on modal open. | Medium | XS | ✅ Done | S7 | Completed S7
17 | UI | QuickAdd dark theme | Full dark theme conversion matching TripDetailModal edit style. | Medium | S | ✅ Done | S7 | Completed S7
18 | UX | Connection description autofill | Selecting OBB connection fills 'Origin → Dest HH:MM TrainName'. | Low | XS | ✅ Done | S7 | Completed S7
19 | UX | Transport type default empty | Forces user to pick; autofills on connection select. | Low | XS | ✅ Done | S7 | Completed S7
25 | Tech Debt | Memoize recentPlaces | useMemo([trips]) in user.tsx | 🔵 Low | XS | ✅ Done | S11 | Completed S11
26 | Tech Debt | Fix floating checkMainQuest promise | await added in handleFavoritePress + handleQuickAddSubmit | 🟡 Medium | XS | ✅ Done | S11 | Completed S11
27 | Tech Debt | Remove getTripById dead code | Removed from services/tripStorage.ts | 🔵 Low | XS | ✅ Done | S11 | Completed S11
28 | Tech Debt | Remove light theme TripRouteFields | theme prop + light styles removed; dark only. | 🔵 Low | XS | ✅ Done | S11 | Completed S11
29 | Tech Debt | Merge screenStyles into user_styles.tsx | root style moved; screenStyles removed from user.tsx | 🔵 Low | XS | ✅ Done | S11 | Completed S11
30 | Tech Debt | Hoist typeIcon() / transportIcon() | Moved to constants/transport.ts as transportIcon() | 🔵 Low | XS | ✅ Done | S11 | Completed S11
31 | Tech Debt | eslint-disable TripRouteFields useEffect | Comment added above mount guard useEffect | 🔵 Low | XS | ✅ Done | S11 | Completed S11
33 | Bug Fix | Rename user_styles to _user_styles.tsx | Expo Router route warning fixed by _ prefix | 🟡 Medium | XS | ✅ Done | S12 | Completed S12
34 | Feature | KlimaTicket presets overhaul | TICKET_GROUPS: 6 nationwide + 20 regional, real 2026 prices. | 🟠 High | S | ✅ Done | S12 | Completed S12
35 | Feature | Delete All Trips slide-to-confirm | SlideToDelete: RNGH Pan + absolute overlay + saveTrips([]) | 🟠 High | M | ✅ Done | S12 | Completed S12

## ⚠️ Gotchas
⚠️ Gotchas, Decisions & Hard-Won Lessons
Non-obvious decisions, platform limitations, and rules that must be followed. Check this sheet before touching any of the listed areas. Primary source for 'lessons learned' and 'known limitations' thesis sections.
Area | The Rule / Decision | Why — full context | What happens if broken | Session discovered | Severity | Thesis angle
Icons in Modals | NEVER use IconSymbol (SF Symbols) inside any Modal or overlay. Use MaterialIcons only. | SF Symbols are powered by iOS's symbol rendering engine, which is unavailable inside React Native's Modal component. Icons silently render as empty/invisible on iOS. | All icons in modals become invisible on iOS. No crash — just blank space where icons should be. | S3 | 🔴 Critical | Platform limitations / iOS-specific bugs
RNGH in RN Modal | RNGH gesture handlers do NOT work inside React Native Modal on iOS. Use absolute View overlay instead. | React Native Modal creates a separate native view hierarchy that RNGH cannot intercept. Any component needing RNGH gestures (LongPress, Pan, etc.) must be rendered as an absolute-positioned View in the main hierarchy. | Gesture callbacks never fire. On web, runOnJS may also break — use .runOnJS(true) + setTimeout wrapper. | S12 | 🔴 Critical | Platform limitations / gesture architecture
Delete All Trips — correct method | Delete All Trips MUST call saveTrips([]), NEVER AsyncStorage.removeItem on any key. | The actual storage key is @travelapp_trips. A legacy @trips key no longer exists. removeItem(@trips) silently does nothing. Worse: removeItem(@travelapp_trips) causes loadTrips() to hit the initialTrips demo data fallback, making it appear the delete didn't work. | Trips appear to not be deleted — demo data returns on next load. Extremely confusing to debug because there is no error. | S12 | 🔴 Critical | Data integrity / storage architecture
Expo Router file naming | Files in app/ prefixed with _ are ignored by the router. Style/utility files MUST start with _. | Expo Router v6 treats every file in app/ as a potential route and emits a missing-default-export warning for files that don't export a component. The _ prefix convention opts a file out of routing. | Console warning: 'Route file missing default export'. Non-fatal but pollutes dev logs. | S12 | 🟡 Medium | Framework conventions
services/ and types/ location | Keep services/ and types/ OUTSIDE the app/ directory. | Expo Router v6 processes all files under app/ as routes. Placing tripStorage.ts or trip.ts inside app/ would create phantom routes (/tripStorage, /trip) with no component, causing warnings and potential navigation bugs. | Phantom routes appear in the router. Missing default export warnings. Potential navigation to blank screens. | S1 | 🟠 High | Project architecture
AsyncStorage XP storage | XP is stored as a string. Always use parseInt(). Seed from trips if result is NaN. | AsyncStorage is string-only. Old versions of the app stored the literal string 'NaN' when XP was never set. parseInt('NaN') returns NaN, not 0. Must guard: if isNaN(xp) → re-seed from all trips. | User sees level 0 and 0 XP despite having logged many trips. XP progress bar shows empty. | S3 | 🟡 Medium | Data persistence gotchas
Palette — no hardcoded hex | Only #fff is permitted as a hardcoded hex value. All other colours must come from Palette or constants/transport.ts. | The 9-colour Palette in constants/Colors.ts is the single source of truth for design consistency. Hardcoded hex values scattered across files make global colour changes impractical. | Visual inconsistencies accumulate. Colour changes for a redesign require grep across all files instead of one edit. | S1 | 🔵 Info | Design system methodology
react-native-gifted-charts | Do NOT add react-native-gifted-charts (or chart libraries with complex peer deps) without testing Metro compatibility first. | gifted-charts caused a Metro bundler resolution error after install in S10. The internal dependency tree conflicted with the Expo managed workflow. No clear fix was found after investigation. Custom View-based bars were implemented in ~1h. | Metro bundler fails to start. No clear error message — requires tracing bundler resolution logs. | S10 | 🟡 Medium | Dependency management
Reanimated v4 peer dependency | react-native-worklets must be explicitly installed as a peer dependency of react-native-reanimated v4. | Reanimated v4 split its worklet runtime into a separate package that is not automatically installed as a transitive dependency by npm. Without it, the bundler throws a missing-module error before rendering any screen. | App crashes at bundle time: 'Cannot resolve react-native-worklets'. No Reanimated animations work. | Pre-S | 🟠 High | Dependency management
Supabase WebSocket (metro.config.js) | The 'ws' package must be shimmed to an empty module in metro.config.js for Supabase Realtime to work in React Native. | Supabase's Realtime client depends on 'ws' (a Node.js WebSocket library) which in turn requires the 'stream' built-in. React Native has no 'stream' module. Shimming 'ws' to empty makes Supabase fall back to the global native WebSocket. | Bundle error: 'Unable to resolve module stream'. App fails to start. | Pre-S | 🟠 High | Platform compatibility
GestureHandlerRootView placement | GestureHandlerRootView must wrap the entire app in app/_layout.tsx, not individual screens. | RNGH requires a single GestureHandlerRootView at the root of the component tree to correctly set up the native gesture recognizer hierarchy. Placing it on individual screens means gestures on other screens may not receive correct priority. | Hold gestures on Favorites may silently fail or conflict with ScrollView on screens not wrapped individually. | S2 | 🟡 Medium | Gesture architecture
checkMainQuest — must await | Always call checkMainQuest() with await inside handleFavoritePress and handleQuickAddSubmit. | checkMainQuest is async (reads AsyncStorage). Without await, the function runs fire-and-forget. If it throws (e.g. AsyncStorage read failure), the error is silently swallowed and the Main Quest celebration never fires. | Main Quest overlay never appears, or appears inconsistently. No error surfaced to the user. | S11 | 🟡 Medium | Async error handling

## 🎯 Milestones
🎯 Milestones & Projections
6 of 7 milestones complete · M7 Production Ready target: 2026-04-12 · ~1 session/day velocity
MILESTONE TRACKER
ID | Milestone | Target Date | Status | Key Deliverables | Blockers | Sessions
M1 | Core MVP | 2026-03-14 | ✅ Complete (100%) | Trip CRUD, AsyncStorage, FinancialOverview savings card, XP/Level system, Favorites hold-to-add | — | S1–S2
M2 | Auth & Onboarding | 2026-03-15 | ✅ Complete (100%) | Supabase auth, dark Login/Register screens, 3-slide onboarding pager, animated splash screen | — | S4
M3 | Full Trip Lifecycle | 2026-03-15 | ✅ Complete (100%) | Trip edit/delete, XP toast, level-up overlay, empty state, user profile, KlimaTicket setting | — | S3, S5
M4 | UX Polish | 2026-03-15 | ✅ Complete (100%) | Shared TripRouteFields, price autofill, suggestions dropdown, swap button, distance estimator | — | S6
M5 | Gamification 2.0 | 2026-03-15 | ✅ Complete (100%) | Quest system (daily/weekly/milestone), 19 achievements × 5 categories, Quests & Achievements screen, Main Quest overlay (2000 XP) | — | S8–S9
M6 | Stats & Insights | 2026-03-16 | ✅ Complete (100%) | Stats screen: 4 stat cards, WeeklyBarChart, Transport Mix, Top Routes, CO₂ with tooltip | — | S10
M7 | Production Ready | 2026-04-12 | ⬜ Planned (0%) | Email confirm re-enabled, onboarding images, App Store assets, bug fixes #36/#37, final QA | Image assets (design work needed), App Store account, fix bugs #36 & #37 | S13+

## ✅ Feature Registry
✅ Complete Feature Registry — All 35 Shipped Features
Every shipped feature with primary file, session delivered, category, and thesis classification. Use for methodology appendix.
# | Feature | Category | Session | Primary Files | Description | XP Impact | Thesis Tag
1 | Trip CRUD | Core | S1 | tripStorage.ts, user.tsx | Add, load, save trips to AsyncStorage. Key: @travelapp_trips | — | Data Architecture
2 | 10 Dummy Seed Trips | Core | S1 | tripStorage.ts | Fallback initial data — PRE-PROD BUG #37 (change to []) | Seeds XP | Data Architecture
3 | FinancialOverview Card | UI | S1 | FinancialOverview.tsx | Collapsible savings card with SVG donut; klimaTicketCost from profile | — | Interface Design
4 | Transport Accent Bars | UI | S1 | user.tsx, _user_styles.tsx | Colour-coded left border on trip cards by transport type | — | Interface Design
5 | XP / Level System | Gamification | S2 | levelSystem.ts, user.tsx | getXPForTrip (base+distance+multiplier), calculateLevel, getLevelTitle | Core | Gamification Theory
6 | UserLevelCard | UI | S2 | UserLevelCard.tsx | Animated XP progress bar with level title and quests entry point | Display | Interface Design
7 | Favorites Hold-to-Add | UX | S2 | user.tsx, _user_styles.tsx | RNGH LongPress 1000ms fill animation to re-add frequent trips | Yes | UX Design
8 | Show All / Show Less Toggle | UI | S2 | user.tsx | Recent Trips list: defaults 5 items; expand/collapse all | — | Interface Design
9 | TripDetailModal (view+delete) | Feature | S3 | TripDetailModal.tsx | Tap trip → view details; delete with in-app confirm overlay; XP subtracted | Delete: −XP | Feature Design
10 | XP Seeding Fix | Bug Fix | S3 | user.tsx, tripStorage.ts | Seeds XP from trips if stored value is NaN or missing | Fixes XP | Bug Analysis
11 | Logout Button | Auth | S3 | user.tsx | Red-bordered button; signOut(); routes to /onboarding | — | Auth Architecture
12 | Safe-Area + UX Overhaul | UX | S3 | user.tsx, _user_styles.tsx | paddingTop:52, loading spinner, section icons, scroll padding | — | UX Design
13 | Supabase Auth | Auth | S4 | supabase.ts, LoginForm, RegisterForm | Real email/password auth with AsyncStorage session persistence | — | Auth Architecture
14 | Dark Login Screen | UI | S4 | login.tsx, LoginForm.tsx | ImageBackground + LinearGradient overlay, Palette dark design | — | Interface Design
15 | Dark Register Screen | UI | S4 | register.tsx, RegisterForm.tsx | Matches login design; success state before redirect to login | — | Interface Design
16 | 3-Slide Onboarding | Onboarding | S4 | onboarding.tsx | FlatList pagingEnabled pager; tappable dots; CTA only on last slide | — | FRE Design
17 | Animated Splash Screen | UX | S4 | index.tsx | Reanimated scale+fade 2s; Supabase session check before routing | — | UX Design
18 | Trip Editing | Feature | S5 | TripDetailModal.tsx | mode:'view'¦'edit'; pre-filled form; XP delta on save (floored at 0) | XP delta | Feature Design
19 | XPToast | Gamification | S5 | XPToast.tsx | Floating '+N XP' badge; Reanimated spring+float; ~1.2s; on every trip add | Display | Gamification Theory
20 | LevelUpOverlay | Gamification | S5 | LevelUpOverlay.tsx | Full-screen celebration; spring-in card; auto-dismiss ~2.8s | Display | Gamification Theory
21 | Empty State | UX | S5 | user.tsx | Icon + message + CTA when no trips logged | — | UX Design
22 | KlimaTicket Cost Setting | Settings | S5 | profile.tsx | Dropdown presets + custom; persisted; drives all break-even calculations | Affects savings | User Configuration
23 | User Profile Screen | Feature | S5 | profile.tsx | Avatar (initials), name input, KlimaTicket picker, danger zone | — | Feature Design
24 | TripRouteFields (shared) | Refactor | S6 | TripRouteFields.tsx | Shared origin/dest/cost/distance/transport component used by both modals | — | Software Quality
25 | Price Autofill | UX | S6 | TripRouteFields.tsx | ROUTE_PRICES + TRANSPORT_FLAT_PRICES; mount guard useRef(false) | — | UX Design
26 | Suggestions Dropdown | UX | S6 | TripRouteFields.tsx | recentPlaces filtered as user types; sorted by frequency; useMemo | — | UX Design
27 | Swap Origin/Destination | UX | S6 | TripRouteFields.tsx | Single tap reverses origin and destination fields | — | UX Design
28 | Distance Estimator | Feature | S6 | TripRouteFields.tsx, oebbApi.ts | Estimate button; haversine on ÖBB station coords × 1.25 detour factor | Affects XP | Feature Design
29 | ÖBB Distance Fix | Bug Fix | S7 | oebbApi.ts | summariseJourney: haversine fallback when HAFAS API returns 0m distance | Fixes 0 XP | Bug Analysis
30 | Price Autofill Mount Fix | Bug Fix | S7 | TripRouteFields.tsx | useRef(false) guard prevents autofill from overwriting user input on open | — | Bug Analysis
31 | QuickAdd Dark Theme | UI | S7 | QuickAddTripModal.tsx | Full dark theme matching TripDetailModal edit mode | — | Interface Design
32 | Connection Description Autofill | UX | S7 | QuickAddTripModal.tsx | Selecting ÖBB connection fills description: 'Origin → Dest · HH:MM · Train' | — | UX Design
33 | Transport Default Empty | UX | S7 | QuickAddTripModal.tsx | Forces explicit user selection; autofills from connection select | — | UX Design
34 | Quest System | Gamification | S8 | utils/questSystem.ts | Daily(8)/weekly(8)/milestone(9) pools; random rotation by date key; XP claim | Quest XP | Gamification Theory
35 | Achievement System | Gamification | S8 | utils/achievementSystem.ts | 19 achievements × 5 categories; computeStreak; computeSavedVsCar | — | Gamification Theory
36 | Quests & Achievements Screen | Feature | S8 | app/quests.tsx | Segmented tabs; QuestCard; AchievementCard; XP claim; deep-link ?tab=achievements | XP on claim | Feature Design
37 | Main Quest Featured Card | Gamification | S8 | app/quests.tsx | Red-border card at top of Quests tab; €X/€Y progress; CLAIM 2000 XP | 2000 XP | Gamification Theory
38 | MainQuestOverlay | Gamification | S8 | MainQuestOverlay.tsx | Full-screen; 6 floating Reanimated stars; spring-in card; one-time @mainQuestCelebrated flag | Display | Gamification Theory
39 | Main Quest Break-Even Detection | Feature | S8 | app/(tabs)/user.tsx | checkMainQuest() after every trip add; compares savings to klimaTicketCost; one-time | Triggers 2000 XP | Feature Design
40 | UserLevelCard Quests Link | UI | S8 | UserLevelCard.tsx | Bottom row with chevron → /quests via onQuestsPress prop | — | Interface Design
41 | Profile Achievements Button | UX | S8 | profile.tsx | Deep-links to /quests?tab=achievements | — | UX Design
42 | Stats & Insights Screen | Stats | S10 | app/stats.tsx | 4 stat cards, CO₂ tooltip, KlimaTicket progress, WeeklyBarChart, Transport Mix, Top Routes | — | Data Visualisation
43 | Stats Entry — Donut | UI | S10 | FinancialOverview.tsx | SVG donut wrapped in TouchableOpacity → /stats via onStatsPress prop | — | Interface Design
44 | Stats Entry — Profile | UX | S10 | profile.tsx | 'Stats & Insights' button → /stats | — | UX Design
45 | KlimaTicket Presets Overhaul | Settings | S12 | profile.tsx | TICKET_GROUPS: 6 nationwide + 20 regional, real 2026 Austrian prices | Affects savings | User Configuration
46 | Delete All Trips Slide | Feature | S12 | profile.tsx | SlideToDelete: RNGH Pan + absolute overlay + saveTrips([]). NOT RN Modal. | Resets XP | Feature Design
47 | PM Updater Script | PM | S8 | pm_updater.py | PMUpdater class; 14 methods; idempotent; ~2min session update vs ~15min manual | — | Development Process