## 📊 Dashboard
🚂 KlimaChallenge — TravelApp ¦ Project Management & Development Diary
Session 12 Complete · 2026-03-16 · React Native / Expo SDK 54 · Supabase · TypeScript
KEY METRICS
Sessions Completed |  | Features Shipped |  | Open Backlog Items |  | Tech Debt Items |  | Pre-Prod Blockers
14 |  | 42 |  | 13 |  | 0 |  | 5
prev sessions: 13 / 39 / 14 / 0 / 3 · Open Backlog = open feature/bug items; Pre-Prod Blockers = separate infra items not counted above
MILESTONE PROGRESS
ID | Milestone |  | Target |  | Status |  | Completion |  | Blocker / Notes
M1 | Core MVP |  | 2026-03-14 |  | ✅ Complete (100%) |  | 100% |  | —
M2 | Auth & Onboarding |  | 2026-03-15 |  | ✅ Complete (100%) |  | 100% |  | —
M3 | Full Trip Lifecycle |  | 2026-03-15 |  | ✅ Complete (100%) |  | 100% |  | —
M4 | UX Polish |  | 2026-03-15 |  | ✅ Complete (100%) |  | 100% |  | —
M5 | Gamification 2.0 |  | 2026-03-15 |  | ✅ Complete (100%) |  | 100% |  | —
M6 | Stats & Insights |  | 2026-03-16 |  | ✅ Complete (100%) |  | 100% |  | —
M7 | Production Ready |  | 2026-04-12 |  | ⬜ Planned (0%) |  | 0% |  | Bugs #36/#37; images; email confirm; App Store
SESSION VELOCITY (features shipped per session)
Session | Date | Key Focus | Features | Category | Cumulative | Bar (max=9)
Pre-S | Mar 13 | Bug triage + SDK 52→54 upgrade | — | Bug Fix / Infra | — | ░░░░░░░░░░
S1 | Mar 14 | Trip CRUD, FinancialOverview, seed data | 4 | Infra / Core | 4 | ████░░░░░░
S2 | Mar 14 | Favorites RNGH, XP/level, UserLevelCard | 3 | UX / Gamification | 7 | ███░░░░░░░
S3 | Mar 15 | TripDetailModal, XP seed fix, UX overhaul | 4 | Bug Fix / UX | 11 | ████░░░░░░
S4 | Mar 15 | Supabase auth, Login/Register, Onboarding | 3 | Auth / Onboarding | 14 | ███░░░░░░░
S5 | Mar 15 | Trip editing, XPToast, LevelUpOverlay, profile, settings | 9 | Features / UX | 23 | ██████████
S6 | Mar 15 | TripRouteFields, price autofill, ÖBB suggestions | 5 | Refactor / UX | 28 | ██████░░░░
S7 | Mar 15 | ÖBB distance fix, QuickAdd dark theme, PM Excel | 7 | Bug Fix / UI | 35 | ████████░░
S8+S9 | Mar 15 | Quest system, achievements, Main Quest — continuous sprint ★ S8 and S9 were a continuous gamification sprint — combined here | 8 | Gamification | 43 | █████████░
S10 | Mar 16 | Stats & Insights screen | 3 | Stats | 46 | ███░░░░░░░
S11 | Mar 16 | Tech debt sprint: 9 items cleared | — | Tech Debt | — | ░░░░░░░░░░
S12 | Mar 16 | KlimaTicket presets, Delete All Trips, 4 bug fixes | 2 | Feature / Bug Fix | 48 | ██░░░░░░░░
S13 | Mar 17 | Bug fixes #36 (quest reset on Delete All) + #37 (remove demo data fallback) | 2 | Bug Fix | 50 | ██░░░░░░░░
S14 | Mar 16 | DateTimePicker + full Trips screen + profile nav rework | 3 | Feature / UX | 53 | ███░░░░░░░

## 📓 Session Diary
📓 KlimaChallenge — Session Diary
Chronological record of every session — decisions, problems, alternatives rejected, lessons learned, and retrospective reflection. Primary source for methodology chapters.
Session | Date | Scope / Theme | What was built — deliverables & files | Why — motivation & design rationale | Problems encountered | Alternatives rejected | Decisions & gotchas for future reference | Features # | Effort est. | Thesis tag | Reflection — with hindsight
Pre-S | 2026-03-13 | Bug triage + SDK 52→54 upgrade | Fixed 5 pre-existing bugs: calculateLevel crash on 0 XP (Math.log(0)=-Infinity), broken transport type matching in XP formula (checking 'bike'/'walk' not 'Bus'/'Train'), trip detail screen showing hardcoded Paris/Tokyo/Bali data, duplicated service code in user.tsx, date picker showing future dates. Upgraded Expo 52→54 (React 18→19, RN 0.76→0.81, expo-router v4→v6). Runtime fixes: Supabase ws shim in metro.config.js, react-native-worklets peer dep, URL polyfill as first import in _layout.tsx, asset paths ./assets/ → ./assets/images/. | App was non-functional before feature work could begin. SDK upgrade sequenced first to establish a clean, modern baseline — expo-router v6 typed routes were required for the auth flow architecture planned in S4, and deferring the upgrade would have risked mid-sprint breaking changes. | Math.log(0) = -Infinity caused level display to break for new users. Supabase 'ws' package requires Node.js 'stream' built-in unavailable in React Native — shimmed to empty module in metro.config.js. react-native-worklets required as explicit peer dep for Reanimated v4 (not pulled in transitively). | Could have deferred SDK upgrade to a later session and built features on SDK 52. Rejected because expo-router v6 typed routes were already planned as a dependency of the S4 auth routing architecture. | URL polyfill must be the first import in _layout.tsx — order matters. Metro.config.js ws shim is load-bearing for Supabase; removing it breaks the bundle. Asset paths must be ./assets/images/ not ./assets/. | — | ~4h | System Setup / Technical Debt | Sequencing the upgrade before feature work was correct — no mid-sprint breakage occurred. The Supabase ws shim in metro.config.js is fragile and undocumented; a future Supabase SDK update could silently break it. In hindsight, this risk should be documented as a known limitation for the production release notes.
S1 | 2026-03-14 | Core MVP — data layer and financial overview | Trip CRUD via AsyncStorage (key: @travelapp_trips). FinancialOverview collapsible savings card with SVG donut. 10 dummy seed trips for development testing. Transport accent bars on trip cards by type. Files: services/tripStorage.ts, app/(tabs)/user.tsx, FinancialOverview.tsx | Established the foundational data loop before any UI polish: add trip → save → reload → display. FinancialOverview built immediately because break-even tracking is the core value proposition, not a decorative feature — it needed to be real from day one to validate the concept. | klimaTicketCost was hardcoded as a constant (€1,297.80, the pre-2026 price) inside FinancialOverview while the prop passed from user.tsx was €1,090 — the prop was silently ignored entirely. The correct 2026 price is €1,400. Both issues resolved in S5 by removing the constant and using the profile-stored value throughout. | Considered SQLite for persistence (more queryable) and Supabase cloud-first storage. Both deferred: SQLite adds complexity without benefit at MVP scale; Supabase sync requires schema design and conflict resolution that would have slowed S1 significantly. | AsyncStorage key @travelapp_trips chosen (not @trips). This specific naming distinction directly caused the S12 Delete All Trips bug — the wrong key was used in a removeItem call, silently doing nothing. | 4 | ~3h | Data Architecture / MVP Design | The data layer was correct and stable throughout the project. However, the @travelapp_trips key name should have been defined as a named constant from the start and imported everywhere — the S12 bug (wrong key in removeItem) was a direct consequence of the key string being hardcoded in multiple places rather than referenced from one source of truth. A single-line change in S1 would have prevented a multi-bug debugging session in S12.
S2 | 2026-03-14 | Gamification core — XP, levels, Favorites hold-to-add | XP/level system: getXPForTrip (base 10 + distance capped 50km × transport multiplier), calculateLevel (exponential curve floor(100×1.5^(n-1))), getLevelTitle (10 named tiers). UserLevelCard with animated Reanimated XP progress bar. Favorites hold-to-add: RNGH LongPress 1000ms + Reanimated fill animation. Show all / Show less toggle on trip list. Files: utils/levelSystem.ts, UserLevelCard.tsx, user.tsx, user_styles.tsx | XP formula designed to reward frequency over distance (base 10 XP for any trip regardless of length) while capping distance contribution at 50km to prevent one long journey dominating the level curve. Transport multipliers incentivise less car-like modes — Tram at 1.4× highest because trams are most distinctly non-car public transport. | Favorites hold gesture failed with 5 successive approaches before RNGH. TouchableOpacity onPressIn: scroll delay. Pressable onPressIn: intercepted by ScrollView native gesture recogniser. onTouchStart on View: same. PanResponder: JS-layer only, loses to native scroll. scrollEnabled toggle: race condition on release. | All five pre-RNGH approaches tried and abandoned in sequence. RNGH chosen because it operates at the native gesture layer and correctly negotiates with ScrollView via GestureHandlerRootView. | GestureHandlerRootView must wrap the entire app in _layout.tsx. Any hold/drag/swipe interaction inside a ScrollView on mobile requires RNGH — JS-layer gesture approaches all fail. | 3 | ~4h | Gamification Design / Gesture Interaction / Behavioural Incentives | The XP formula has worked well and needed no revision. The RNGH decision was correct, but the constraint it created — RNGH cannot live inside React Native Modal — was not discovered until S12, costing significant debugging time. In hindsight, the Modal constraint should have been tested in S2 as a deliberate edge case rather than discovered accidentally ten sessions later. The five-failure sequence is strong thesis evidence of systematic platform exploration.
S3 | 2026-03-15 | Trip lifecycle — detail view, delete, XP seeding | TripDetailModal: tap trip to view details, delete with in-app confirm overlay (not system dialog), XP subtracted on delete (floored at 0). XP seeding fix: seeds from all trips if stored value is missing or 'NaN'. Logout: red-bordered button, supabase.auth.signOut(), routes to /onboarding. User page overhaul: paddingTop 52, loading spinner, section icons, transport accent bars, show-all/show-less toggle. Files: TripDetailModal.tsx, user.tsx, tripStorage.ts | Delete confirmation as in-app overlay keeps visual language consistent with the dark Palette theme — system dialogs cannot be styled. XP seeding fix was critical: users with pre-existing trips would see level 0 XP on upgrade because the 'userXP' key had never been set. | SF Symbols (IconSymbol component) silently render as empty/invisible inside React Native Modal on iOS. Discovered during TripDetailModal implementation — all icons were invisible in testing. | System confirm dialog (Alert.alert) considered for delete — rejected because it cannot be styled and breaks visual consistency. | STANDING RULE established: always use MaterialIcons inside any Modal or overlay. IconSymbol / SF Symbols are unreliable in Modal on iOS. This rule applies for the entire remaining project. | 4 | ~3h | UX Design Decisions / Platform Limitations | The MaterialIcons-in-modals rule discovered here is the clearest example of an iOS platform limitation that is not documented in the React Native official docs. The rule was added to memory files but not consulted before the S12 SlideToDelete implementation — which then triggered the RNGH-in-Modal discovery. Both platform limitations (SF Symbols in Modal and RNGH in Modal) point to a general principle: React Native Modal creates an isolated native view hierarchy that breaks many interaction systems. In hindsight, Modal should be treated as a last resort, not a default container.
S4 | 2026-03-15 | Auth & First Run Experience — full FRE architecture | Real Supabase auth: signInWithPassword, signUp with name metadata. lib/supabase.ts singleton with AsyncStorage session persistence. Dark Login screen: ImageBackground + LinearGradient, Austrian map. Dark Register screen matching login. 3-slide Onboarding FlatList pager with tappable dots and skip. Animated splash: Reanimated scale+fade 2s, Supabase session check before routing. Files: login.tsx, register.tsx, onboarding.tsx, index.tsx, supabase.ts, LoginForm.tsx, RegisterForm.tsx | Login moved outside tab group (app/login.tsx) because (1) auth screens should not be tabs — they are pre-authentication content, and (2) adding a root app/index.tsx splash screen created a routing conflict: in expo-router v6, (tabs)/index.tsx and app/index.tsx both resolve to '/', making one unreachable. router.replace() used for onboarding→login navigation so the back button cannot return to onboarding slides from login. | Routing conflict: (tabs)/index.tsx and app/index.tsx both resolve to '/' in expo-router v6 — only one can exist. Required full FRE architecture decision before any screens could be built. | Option A: rename (tabs)/index.tsx to (tabs)/home.tsx (minimal change, but login still inside tabs). Option B: handle all FRE logic in _layout.tsx (no extra files, but complex layout logic). Option C (chosen): move login entirely outside tabs into app/login.tsx — most architecturally correct, tab group = authenticated only. | Email confirmation disabled in Supabase dashboard for dev. MUST re-enable before production — this is a pre-prod blocker. Session check via supabase.auth.getSession() not AsyncStorage flag. | 3 | ~5h | Auth Architecture / FRE Design / Routing Design | The Option C architecture has proven completely correct — the tab group being 'authenticated only' has simplified every subsequent auth-related decision by giving it a clear rule to follow. Options A and B would have required revisiting auth-gating logic repeatedly. The routing conflict that forced this decision was actually a productive constraint: it required making the architecture explicit rather than leaving it ambiguous. The disabled email confirmation remains a pre-prod risk that must not be forgotten.
S5 | 2026-03-15 | Trip editing, XP feedback animations, profile — 9 features | Trip editing in TripDetailModal: mode:'view'¦'edit', pre-filled form, XP delta on save (new XP − old XP, floored at 0). XPToast: floating '+N XP' badge, Reanimated spring+float, 1.2s. LevelUpOverlay: full-screen, spring-in card, auto-dismiss 2.8s. Empty state for no trips. KlimaTicket cost setting: dropdown presets persisted. User profile screen: avatar (initials), name, KlimaTicket picker. Files: TripDetailModal.tsx, user.tsx, XPToast.tsx, LevelUpOverlay.tsx, profile.tsx, levelSystem.ts | XP delta on edit ensures XP always reflects actual logged data — without it, editing a trip to increase distance would not award the extra XP. KlimaTicket cost as a user setting rather than hardcoded fixed value was the permanent fix for the S1 bug where the €1090 prop was ignored. | Highest-density session (9 features). The XP delta logic requires careful floor-at-zero handling: if new XP < old XP (e.g. editing a trip to reduce distance), the delta is negative and must be subtracted, but total XP must never go below zero. | Separate edit screen (router.push to a new route) considered — rejected to keep the trip detail interaction self-contained in one modal. Inline mode switching keeps context clearer. | getLevelTitle() must be a shared export from levelSystem.ts — both UserLevelCard and LevelUpOverlay need it. XP delta: always clamp total XP at 0, never allow negative. | 9 | ~6h | Gamification Loop Design / Animation UX / Feedback Mechanisms | 9 features in one session is very high velocity and introduces risk. In this case, no regressions were introduced, but the pattern is not advisable as a general approach. The XP delta logic (never below zero) was implemented correctly but never got a dedicated test — an edge case like deleting a trip that was part of a level-up could theoretically produce unexpected state. In hindsight, the high-velocity sessions (S5, S6, S7) accumulated the tech debt that S11 was entirely spent clearing.
S6 | 2026-03-15 | Shared TripRouteFields component and ÖBB autofill | TripRouteFields shared component: origin, destination, cost, distance, transport picker — used by both QuickAdd and TripDetailModal edit mode. Price autofill: ROUTE_PRICES (city pairs) + TRANSPORT_FLAT_PRICES (fallback). Recent places suggestions dropdown (useMemo). Swap button. Distance estimator: haversine × 1.25 detour factor. Files: TripRouteFields.tsx, oebbApi.ts, QuickAddTripModal.tsx, TripDetailModal.tsx | Before this session QuickAdd and TripDetailModal edit mode had separate copies of the route input logic. Extraction eliminated duplication and ensured identical autofill behaviour in both flows. Static ROUTE_PRICES chosen because the HAFAS proxy returns no ticket prices (known limitation). | Price autofill mount guard: without a useRef(false) guard, the useEffect fired on modal open and overwrote user-entered cost values with autofilled amounts. Pattern fix: useRef(false) skips first render. | Live pricing via ÖBB Scotty API or VAO API researched but not pursued — auth complexity and unclear availability. Static ROUTE_PRICES table chosen as pragmatic interim solution. | useRef(false) mount guard pattern for any useEffect that should only fire on user-driven changes, not initial render. haversine × 1.25 as standard detour factor throughout the app. | 5 | ~5h | Component Architecture / API Integration / UX Patterns | TripRouteFields extraction was the right refactoring decision — it was used in both modals without issue for the remainder of the project. The ROUTE_PRICES table is still limited to Villach routes and should be expanded before release. The static pricing approach is a known limitation that the Pricing API Research backlog item addresses — this should be resolved before production, as accurate cost data is central to the app's value proposition.
S7 | 2026-03-15 | ÖBB distance fix, QuickAdd dark theme, PM setup | ÖBB distance fix: summariseJourney haversine fallback when HAFAS API returns 0m distance. QuickAdd fully converted to dark theme. Connection description autofill: 'Origin → Dest · HH:MM · TrainName'. Transport type defaults to empty — forces explicit user selection, autofills on connection select. 400ms debounce on ÖBB station search. KlimaChallenge_PM.xlsx and pm_updater.py created. Files: oebbApi.ts, TripRouteFields.tsx, QuickAddTripModal.tsx | ÖBB distance bug caused all connection-sourced trips to earn 0 XP — trips logged via the connection search were silently earning nothing. Debounce added because each keystroke was firing a network request to the HAFAS proxy, causing lag and unnecessary load. | HAFAS API returns connections as {journeys, fromStation, toStation} but the journey distance field is often 0 or missing — required fallback to haversine on station lat/lng coordinates. | ÖBB Scotty API and VAO API both explored as proxy alternatives — neither pursued due to auth requirements. macistry.com proxy remains the only functioning solution found. | 400ms debounce (not 300ms) — slightly more settled feel on mobile keyboards. PM Excel created explicitly to support thesis documentation as a secondary deliverable of this session. | 7 | ~5h | API Integration / Development Process / Tooling | The ÖBB distance fix was important but revealed a deeper issue: the dependency on macistry.com is a single point of failure with no SLA. If the proxy changes its response format or goes offline, the connection search breaks silently. In hindsight, the oebbApi.ts service should have error boundaries that gracefully degrade to manual entry rather than failing. This is worth noting in the thesis as a known limitation of third-party API dependency in solo development.
S8 | 2026-03-15 | Full gamification loop — quests, achievements, Main Quest | Quest system: daily pool (8), weekly pool (8), milestone pool (9). Random rotation via pickRandomQuests; stored in AsyncStorage by date/week key. getClaimKey, timeUntilMidnight, daysUntilMonday helpers. Achievement system: 19 achievements × 5 categories; computeStreak, computeSavedVsCar helpers. Quests & Achievements screen with segmented control, QuestCard, AchievementCard, XP claim. MainQuestFeaturedCard and MainQuestOverlay (6 floating Reanimated stars, spring-in, one-time). Files: questSystem.ts, achievementSystem.ts, quests.tsx, MainQuestOverlay.tsx, user.tsx, UserLevelCard.tsx, profile.tsx | Quest rotation uses date/week key so the selection is stable within a period (same quests all day) but randomly changes at midnight/Monday — this creates a variable reward schedule that drives return visits without allowing gaming via app refresh. Main Quest is the emotional climax of the app — the moment break-even is reached. The 2000 XP reward signals it as categorically different from routine quests. | checkMainQuest() was initially called without await — async errors were silently swallowed and the celebration could miss-fire on slow devices. Fixed in S11 with explicit await in both call sites. | Fixed quest set (no rotation) considered — rejected as users would exhaust the quest list within a week and lose motivation. Fully random on each app open also rejected — instability would prevent users from tracking progress on a quest across a day. | One-time @mainQuestCelebrated flag is critical — the overlay must never fire twice. The 2000 XP reward must be claimed via the quests screen, not auto-awarded, to maintain user agency. | 8 | ~6h | Gamification Theory / Motivation Design / Reward Schedules | The quest rotation design (stable-within-period, random across periods) was a well-reasoned decision grounded in behavioural theory, and it has worked as intended. The floating promise bug (checkMainQuest without await) is a good example of how async code in event handlers requires deliberate audit — this should be documented as a development pattern recommendation in the thesis methodology section. The achievement categories align closely with self-determination theory dimensions (competence, relatedness, autonomy) which is worth making explicit in the gamification chapter.
S10 | 2026-03-16 | Stats & Insights screen | app/stats.tsx: 4 stat cards (trips, distance, CO₂ saved at 0.16 kg/km, avg cost/trip). CO₂ long-press tooltip with methodology. KlimaTicket progress bar. WeeklyBarChart: custom View-based, 8 ISO weeks. Transport Mix: horizontal proportional bars, colour-coded by type. Top Routes: ranked list, top 5 by trip count. Entry points: FinancialOverview donut (onStatsPress prop) + profile button. Files: app/stats.tsx (new), FinancialOverview.tsx, profile.tsx | CO₂ factor of 0.16 kg/km derived from car average (0.21) minus public transport average (0.05) — displayed as 'saved vs driving' to make it legible without requiring users to understand absolute emissions figures. Custom View-based chart chosen after react-native-gifted-charts caused an unresolvable Metro bundler conflict. | react-native-gifted-charts: Metro could not resolve one of its internal peer dependencies after install. No clear fix found after investigation. Custom View-based bars implemented as replacement in approximately one hour. | react-native-gifted-charts tried first. Victory Native also considered but carries the same Metro conflict risk. Custom Views chosen as zero-dependency solution with full styling control. | WeeklyBarChart uses ISO week numbers as keys — important for correct Monday-start week boundaries in Austria/Europe. CO₂ long-press tooltip avoids cluttering the stat card. | 3 | ~4h | Data Visualisation / Sustainability Metrics / Eco-Feedback Systems | Custom charts were the right call and took less time than debugging the library. The CO₂ factor (0.16 kg/km) is used without a cited source — for the thesis this needs an academic or government reference (e.g. Austrian Federal Environment Agency transport emission factors). This is a minor but important academic rigour gap. Victory Native should be reconsidered post-launch if richer chart types are needed — it has better Expo support than gifted-charts.
S11 | 2026-03-16 | Dedicated tech debt clearance sprint | 9 debt items: useMemo([trips]) for computeFavorites + recentPlaces. constants/transport.ts: TRANSPORT_COLOR + transportIcon() as single source of truth. await added to checkMainQuest() call sites. getTripById() dead code removed. Light theme removed from TripRouteFields. screenStyles merged into _user_styles.tsx. typeIcon() moved to transportIcon() in transport.ts. eslint-disable comment on TripRouteFields useEffect mount guard. Project memory files added to git at .claude/memory/. Files: constants/transport.ts (new), user.tsx, stats.tsx, TripRouteFields.tsx, QuickAddTripModal.tsx, _user_styles.tsx, tripStorage.ts | Dedicated debt sprint before S12 features — technical debt accumulates fastest in high-velocity sprints (S5–S9 shipped 35 features in 4 days). Memory files added to git so project context is portable across devices and version-controlled as a development artefact in its own right. | No significant technical problems — this was planned remediation. The batching of 9 items was efficient but also revealed that the debt had been allowed to accumulate across 6 sessions. | Could have cleared debt incrementally at the end of each session (15-minute debt check pattern). Chosen to batch for efficiency, but the batch approach means the codebase was carrying debt for several sessions longer than it needed to. | Transport constants centralised: user.tsx and stats.tsx had independent colour maps that could diverge. Single source of truth in constants/transport.ts prevents this class of inconsistency. | — | ~3h | Software Quality / Refactoring Methodology / Technical Debt Management | The debt sprint was necessary and valuable, but in hindsight the 'batch all debt' pattern has a cost: the codebase carried known issues for multiple sessions. A more disciplined approach would be a short debt review at the end of each session (even 15 minutes) rather than a full sprint every 5-8 sessions. The memory-to-git decision was important for this thesis — version-controlled memory files mean the development process itself is documented and auditable, which strengthens the methodology chapter considerably.
S12 | 2026-03-16 | KlimaTicket presets overhaul + Delete All Trips | KlimaTicket presets: TICKET_GROUPS with 6 nationwide + 20 regional variants, all real 2026 Austrian prices. Grouped dropdown with section headers and description field. Delete All Trips slide-to-confirm: SlideToDelete using RNGH Gesture.Pan().runOnJS(true), absolute-positioned overlay (NOT RN Modal). saveTrips([]) to clear. useFocusEffect reloads trips+XP on screen focus. Bug fixes: typeIcon() crash in stats.tsx, Expo Router warning for user_styles.tsx → renamed _user_styles.tsx. Files: profile.tsx, stats.tsx, user.tsx, _user_styles.tsx | Real 2026 KlimaTicket prices were needed for accurate break-even calculations — the app's core value proposition. Slide-to-confirm for an irreversible action follows iOS Human Interface Guidelines on destructive action confirmation: higher friction for higher stakes. | Three compounding bugs in Delete All Trips: (1) RNGH gestures dead inside RN Modal on iOS — fixed by using absolute View overlay. (2) runOnJS broken on web — fixed with .runOnJS(true) + setTimeout. (3) Wrong key: removeItem(@trips) would not clear @travelapp_trips AND caused initialTrips fallback to reappear — fixed by calling saveTrips([]) with the correct key. | Simple confirmation button/dialog considered — rejected because the irreversibility of deleting all trips warrants higher-friction UX. Modal dismissed as container for gestures after S3 established the MaterialIcons-in-Modal rule — but the broader RNGH-in-Modal constraint was not consulted until the bug appeared. | CRITICAL: Delete All Trips must call saveTrips([]) not removeItem. RNGH Pan gestures must use absolute View overlay, never RN Modal. Expo Router ignores files prefixed with _ in app/ directory. | 2 | ~4h | UX Patterns / Platform Bug Analysis / Debugging Methodology | The three compounding bugs in S12 are the clearest example in the project of how undocumented platform constraints compound. The RNGH-in-Modal constraint was implicitly known from S2 (when RNGH was chosen over JS-layer gestures) but never explicitly documented as a rule until it was rediscovered as a bug. The storage key bug traces back to the S1 decision to use @travelapp_trips without defining it as a constant. Both bugs were preventable with better upfront documentation discipline. This session is strong thesis evidence for the argument that explicit decision logging — the primary purpose of this file — has concrete preventative value in solo development projects.
S13
S14 | 2026-03-16 | Native DateTimePicker · Trips list screen · Profile layout rework | #42 DateTimePicker: replaced custom 7-day date scroll + manual HH:MM inputs with @react-native-community/datetimepicker in both QuickAddTripModal and TripDetailModal. iOS: spinner display inline + Done button. Android: system dialog. Single Date state (no hour/minute strings). Plugin added to app.config.ts. Requires custom dev build (not Expo Go). Recent Trips rework: main screen now groups preview trips by date (date group headers). New app/trips.tsx screen: filter chips (All/Bus/Train/Tram/Subway), full date-grouped list, swipe-left-to-delete (RNGH Pan, -80px threshold, red zone, 200ms fly-off). 'See all X trips' navigates to /trips. New utils/tripGrouping.ts shared helper (formatDateLabel, groupTripsByDate). Deleted dead stubs app/new-trip.tsx + app/trip/[id].tsx. Profile rework: new layout order — Avatar → Display Name + KlimaTicket + Save → navSection (Stats / Achievements / My Trips) → Danger Zone. My Trips button added (MaterialIcons format-list-bulleted, routes to /trips). Files: app.config.ts, components/ui/QuickAddTripModal.tsx, components/ui/TripDetailModal.tsx, app/(tabs)/user.tsx, app/(tabs)/_user_styles.tsx, app/trips.tsx (new), app/profile.tsx, utils/tripGrouping.ts (new) | DateTimePicker: users had no way to backfill past trips — critical real-world usage gap. Trips screen: inline 'show all' expansion had no filter/delete; a dedicated screen matches the mental model of a full trip history. Profile rework: display name + KlimaTicket were buried below nav shortcuts; moving them above improves discoverability and data-entry flow. | CRLF + 4-tab indentation in user.tsx and profile.tsx caused Edit tool to repeatedly fail string matching. Diagnosed with cat -A, resolved by writing complete file rewrites. Typo in user.tsx Write (missing } in JSX) caused cascade of TS parse errors — fixed with targeted edit. theme='dark' prop removal from TripRouteFields caused TS error (prop removed in S11 tech debt). | DateTimePicker: expo-datetime-picker considered but requires native module build anyway; @react-native-community/datetimepicker chosen as more stable and widely used. Trips screen: ScrollView-based swipe vs RNGH Pan — RNGH chosen for correct gesture priority negotiation with parent ScrollView (activeOffsetX + failOffsetY). | DateTimePicker requires custom dev build — document in project state. Swipe card needs opaque backgroundColor (blue.dark) to hide semi-transparent card bleed over red delete zone. Cross-screen sync: trips.tsx writes directly to AsyncStorage; user.tsx picks up via useFocusEffect (no shared state needed). CRLF files must be fully rewritten — Edit tool cannot reliably match Windows line endings. | 3 | ~5h | UX Design / Interaction Design | [To be completed via web interface]
Column colour guide: E (green) = Why / rationale · F (red) = Problems · H (blue) = Standing decisions · L (purple) = Retrospective reflection

## 📐 Decision Log
📐 Architecture Decision Records (ADRs)
Every decision point where two or more viable paths existed — the options evaluated, criteria used, and reversal cost. Use for 'Design Decisions' and 'Methodology' thesis chapters.
# | Decision Area | Context — what forced this decision | Options considered | Decision made & rationale | Criteria used to decide | Reversal cost — what changes if wrong | Session
1 | Auth & Routing Architecture | Adding a root splash screen (app/index.tsx) created a URL conflict with (tabs)/index.tsx — in expo-router v6, both files resolve to '/', making one permanently unreachable. The FRE architecture had to be redesigned before any screens could be built. | Option A: Rename (tabs)/index.tsx to (tabs)/home.tsx — minimal change but login stays inside the tab group as pre-auth content. Option B: Handle all FRE logic in _layout.tsx with conditional rendering — no extra files but complex layout logic. Option C: Move login entirely outside tabs into app/login.tsx. | Option C chosen. The tab group (app/(tabs)/) now contains only authenticated screens. The pre-auth flow (splash → onboarding → login) lives entirely outside the tab group as top-level routes. | Architectural correctness: auth screens should not be tabs. Future-proofing: 'tab group = authenticated only' is a simple rule that requires no per-screen auth checking. Clean URL structure for deep linking. | Would require restructuring all pre-auth screens back into the tab group and re-adding auth gates to every authenticated screen individually. High cost — this decision is now foundational to the entire routing structure. | S4
2 | Navigation Pattern — Hidden Tab Bar | Standard Expo Router tab navigator shows a bottom navigation bar by default. The design intent was to have the main screen (user.tsx) as the unambiguous home base, with secondary screens (stats, quests, profile) feeling like 'drilling in', not 'switching context'. A visible tab bar implies parallel equal sections, which contradicts this hierarchy. | Option A: Standard multi-tab bottom navigation with visible tab bar — conventional, expected by users, free navigation between tabs. Option B: Single tab with hidden tab bar — all navigation via router.push() from the main screen. | Option B chosen. Tab bar hidden via tabBarStyle: {display:'none'}. A single tab screen (user.tsx) is the authenticated root. Stats, quests, and profile are stack-routed screens. This was a primary design decision from which the stack navigation architecture follows as a rational consequence. | Design preference: no visible tab bar. Single clear home base. Secondary screens feel contextually 'deeper' not 'parallel'. Matches the app's identity as a focused tracker, not a multi-section dashboard. | Would require converting router.push() navigation to tab switching, restructuring stats/quests/profile from stack screens to tab screens, and redesigning the entry point UX for each. Medium cost. | S1
3 | Favorites Hold Gesture Implementation | The Favorites section required a hold-to-add interaction (press and hold for 1 second to re-add a trip). On mobile, this gesture must coexist with a ScrollView that owns touch priority by default. Any approach that operates only in the JavaScript layer loses to the ScrollView's native gesture recogniser. | TouchableOpacity onPressIn — scroll delay. Pressable onPressIn — intercepted by ScrollView. onTouchStart on View — same interception. PanResponder — JS-layer only, loses to native scroll. scrollEnabled toggling — race condition on release. RNGH GestureDetector + Gesture.LongPress() — native gesture layer. | RNGH chosen after systematic testing of all five JS-layer approaches. RNGH operates at the native gesture layer and correctly negotiates priority with ScrollView via GestureHandlerRootView at the app root. | Must work reliably on mobile (not just simulator). Must not block normal scrolling. Must be cancellable (release early = no action). Must work alongside Reanimated for fill animation. | Removing RNGH would break the Favorites gesture entirely — no JS-layer replacement exists that works in a ScrollView on mobile. Additionally, the S12 SlideToDelete also uses RNGH Pan, so removal would break two features. GestureHandlerRootView at the app root is a hard dependency. | S2
4 | XP Formula Design | The XP formula needed to reward the behaviours the app is trying to encourage: using public transport frequently, for any distance, and preferring less car-like modes. The formula had to be simple enough to be legible to users while producing meaningful level progression. | Flat XP per trip (no distance or type weighting) — simple but ignores trip quality. Purely distance-based — rewards long journeys only, discourages short trips. Purely frequency-based — ignores transport type. Hybrid with type and capped distance (chosen). | base 10 XP + min(distance, 50km) × transport multiplier (Tram 1.4×, Subway 1.3×, Train 1.2×, Bus 1.1×), rounded. Base 10 ensures any trip earns XP. Cap at 50km prevents one long journey from dominating. Tram highest multiplier because trams are most distinctly non-car public transport. | Frequency rewarded (base XP for any trip). Distance contribution bounded (cap at 50km). Mode diversity incentivised (multipliers). Formula legible to users without documentation. | Changing the formula retroactively would invalidate all existing XP scores. Would require either a migration (recalculate all stored XP from trip history) or a versioned formula with separate rules per period. High retroactive cost — formula should be considered stable for the lifetime of v1. | S2
5 | Quest Rotation Strategy | A static quest set would be exhausted within a week, killing re-engagement. Fully random selection on each app open would be unstable — users could not track progress on a quest across a day. The system needed to create novelty (motivation to return) while maintaining stability (ability to complete a quest across sessions). | Fixed quest set — simple, no rotation logic, but exhausted quickly. Fully random on each app open — maximum novelty, no stability. Stable-within-period random rotation — random at period boundary, stable within the period (chosen). | Stable-within-period rotation: random selection stored in AsyncStorage keyed by current date (daily) or Monday date (weekly). Same quests all day/week. New random selection at midnight/Monday. This creates a variable reward schedule — the quests will change but the user does not know exactly when. | Prevents gaming (can't refresh for easier quests). Provides novelty (new quests each period). Enables within-period progress tracking. Algorithmically simple (just date-keyed AsyncStorage). | Changing the rotation logic would invalidate stored selections. Users mid-quest would have their progress interrupted. Low-to-medium cost if done at a period boundary (midnight/Monday). | S8
6 | Delete All Trips — Confirmation Pattern | Delete All Trips is an irreversible action with no undo. The confirmation mechanism needed to be proportionate to the stakes — high enough friction to prevent accidental activation, clear enough to communicate the consequence. | Simple confirmation button with an Alert.alert system dialog — standard pattern, easy to implement, but cannot be styled. Slide-to-confirm gesture (chosen) — higher friction, fully custom styled, follows iOS HIG for destructive actions. | Slide-to-confirm chosen. SlideToDelete uses RNGH Gesture.Pan() rendered as an absolute-positioned View overlay (NOT RN Modal). On completion, saveTrips([]) writes an empty array to @travelapp_trips. | Friction proportionate to irreversibility. Styled to match dark Palette. Cannot be triggered accidentally. Provides clear visual progress indicator of the action being taken. | Reverting to a simple Alert.alert would be a 1-hour change. However, the RNGH-in-Modal constraint discovered during implementation added an architectural rule (absolute overlay over Modal) that should be preserved regardless of which confirmation UI is used. | S12
7 | Trip Persistence — AsyncStorage vs SQLite vs Supabase | Trip data needed local persistence from day one. Three options existed with very different complexity/capability tradeoffs. The choice would have downstream consequences for querying, cloud sync, and data migration. | AsyncStorage (key-value, JSON) — simplest, no schema, fast to implement, limited queryability. SQLite (relational) — queryable, more complex setup, requires a library (expo-sqlite). Supabase cloud-first — requires auth and schema upfront, enables cross-device sync immediately. | AsyncStorage chosen for MVP. Supabase sync explicitly deferred to post-MVP as backlog item #39. SQLite not pursued — queryability not required at MVP stage; all filtering done in-memory in TypeScript. | Speed to working MVP. No dependency on network availability. No schema design required upfront. Reversible with migration path. | Moving to Supabase (backlog #39) requires: table schema design, upsert-on-save, fetch-on-login, conflict resolution for offline edits. Medium-to-high cost. The migration path is clear but non-trivial. | S1
8 | Stats Chart — Library vs Custom Views | The Stats screen needed a weekly bar chart. A third-party charting library would provide richer visuals faster, but introduces a dependency risk in the Expo managed workflow where Metro bundler compatibility is not guaranteed for all packages. | react-native-gifted-charts — tried first; caused unresolvable Metro bundler conflict after install. Victory Native — considered but carries identical Metro conflict risk. Custom View-based implementation — zero dependencies, full control, more implementation work. | Custom View-based WeeklyBarChart chosen after gifted-charts failure. Horizontal Transport Mix bars also custom. Implementation took approximately 1 hour versus ~30 minutes of failed library debugging. | Zero Metro bundler risk. Full styling control to match Palette. No new dependencies to maintain. Sufficient complexity (bar charts, proportional bars) achievable with plain Views. | Replacing custom charts with a library is straightforward if a Metro-compatible one is found. Low reversal cost — the chart components are isolated in stats.tsx. | S10
9 | ÖBB API — macistry.com Proxy vs Official API | Connection search requires station data and journey connections from ÖBB (Austrian Federal Railways). A direct public official API would be ideal, but investigation found that ÖBB does not publish a public API accessible without institutional credentials. The macistry.com HAFAS proxy was the only functioning solution discovered. | Official ÖBB API — investigated; no public API found that could be accessed without institutional/commercial credentials. ÖBB Scotty API / VAO — candidates on backlog; not yet evaluated for auth requirements. macistry.com HAFAS proxy — functional, no pricing data returned, third-party dependency with no SLA. | macistry.com proxy chosen as pragmatic interim. This is a constrained decision — not a preference between equals, but the only viable option discovered. The Pricing API Research backlog item (#7) should be resolved before production release. | Functional connection search. Station autocomplete. No auth overhead. Accepts that pricing will be unavailable until a better API is found. | Replacing the proxy with an official API requires: new service in oebbApi.ts, response format mapping, auth handling. Medium cost, but the service layer abstraction (oebbApi.ts) means changes are localised. This should be treated as a pre-production task, not a post-launch one. | S6
10 | SDK Upgrade Timing — Before vs After Feature Work | The project was on Expo SDK 52 when feature development began. SDK 54 was available with React 19, RN 0.81, and expo-router v6 typed routes. The upgrade could be done first (clean baseline) or deferred (build features first, upgrade later). | Upgrade first, then build — ~4h upfront investment, no mid-sprint breaking changes, features built on modern foundation. Build first, upgrade later — faster initial feature velocity, risk of breaking changes mid-development, migration debt at the end. | Upgrade first. expo-router v6 typed routes were already planned as a dependency of the auth routing architecture, so the upgrade was not truly optional — it was a prerequisite for the S4 FRE design. | Avoid mid-sprint breaking changes. Access to expo-router v6 features required for auth flow. Reanimated v4 useSharedValue improvements needed for planned animations. | Irreversible — staying on SDK 52 was viable at the pre-session stage but would have required different solutions for auth routing and animation. After the upgrade, no realistic downgrade path exists. | Pre-S
11 | Development Memory System — Dual-Location Sync | Claude Code sessions have no persistent memory by default. Project context must be maintained manually between sessions. A memory system was needed that would be both automatically usable by Claude Code (system path) and version-controlled for portability and auditability (project git path). | System path only (C:\Users\...\memory\ ) — auto-written by Claude Code, not version-controlled, not portable across devices. Git project path only (.claude/memory/) — version-controlled, portable, but not auto-read by Claude Code. Both in sync (chosen) — full capabilities of each. | Both locations maintained in sync. Every memory update writes to the system path (so Claude Code can read it automatically) AND the git project path (so it is version-controlled and portable). Added to git in S11. | Claude Code must be able to load context automatically at session start. Memory must survive across machines (git portability). Memory must be auditable as a development artefact for the thesis. | Dropping one location breaks either auto-loading or portability. The sync discipline (always update both) is a process cost but the only approach that provides both properties simultaneously. | S11

## 📋 Backlog
📋 KlimaChallenge — Backlog
Priority-ordered work queue — open items first, pre-prod checklist second, completed archive below.
OPEN — Work Queue (priority order)
# | Category | Task | Description | Priority | Effort | Status | Target | Notes
36 | Bug Fix | Delete All — reset quests/achievements | handleDeleteAllTrips clears trips+XP but NOT @claimedQuests, @claimedAchievements, @dailyQuestSelection, @weeklyQuestSelection. Stale claimed state persists after reset. | 🔴 Critical | XS (30m) | ✅ Done | S13 | Add AsyncStorage.multiRemove for all 4 keys in handleDeleteAllTrips in profile.tsx · Completed S13 — AsyncStorage.multiRemove(['@claimedQuests','@claimedAchievements','@dailyQuestSelection','@weeklyQuestSelection']) in handleDeleteAllTrips · Completed S13 — AsyncStorage.multiRemove for all 4 quest/achievement keys in handleDeleteAllTrips · Completed S13 — AsyncStorage.multiRemove for all 4 quest/achievement keys in handleDeleteAllTrips · Completed S13 — AsyncStorage.multiRemove for all 4 quest/achievement keys in handleDeleteAllTrips · Completed S13 — AsyncStorage.multiRemove for all 4 quest/achievement keys in handleDeleteAllTrips
37 | Bug Fix | Remove initialTrips demo fallback | loadTrips() returns 10 hardcoded dummy trips when @travelapp_trips key is absent. New users see fake data on first launch. Pre-prod blocker. | 🔴 Critical | XS (15m) | ✅ Done | S13 | Change fallback from `return initialTrips` to `return []` in tripStorage.ts · Completed S13 — Changed fallback from `return initialTrips` to `return []` in tripStorage.ts · Completed S13 — Changed fallback from `return initialTrips` to `return []` in tripStorage.ts · Completed S13 — Changed fallback from `return initialTrips` to `return []` in tripStorage.ts · Completed S13 — Changed fallback from `return initialTrips` to `return []` in tripStorage.ts · Completed S13 — Changed fallback from `return initialTrips` to `return []` in tripStorage.ts
38 | UX | Profile dropdown — close on outside tap | KlimaTicket dropdown stays open when tapping outside. Should close on any outside touch. | 🟡 Medium | XS (30m) | ✅ Done | S13 | TouchableWithoutFeedback wrapper or onStartShouldSetResponder pattern · Completed S13 — Absolute TouchableWithoutFeedback overlay (zIndex 10) closes dropdown; dropdown sits at zIndex 11 · Completed S13 — Absolute TouchableWithoutFeedback overlay (zIndex 10) closes dropdown; dropdown sits at zIndex 11 · Completed S13 — Absolute TouchableWithoutFeedback overlay (zIndex 10) closes dropdown; dropdown at zIndex 11 · Completed S13 — Absolute TouchableWithoutFeedback overlay (zIndex 10) closes dropdown; dropdown at zIndex 11
39 | Feature | Cloud sync for trips (Supabase) | Trips stored AsyncStorage-only — new device login starts from scratch. No cross-device continuity. | 🟠 High | L (1-2d) | ⬜ Todo | Any | Requires Supabase trips table schema, upsert on save, fetch on login, conflict resolution
40 | Feature | Trip export / CSV download | Allow users to export all trips as CSV for tax/Jobticket employer reimbursement purposes. | 🔵 Low | S (2-4h) | ⬜ Todo | Any | expo-sharing + expo-file-system to write and share CSV file
— | Research | Pricing API investigation — pre-release priority | macistry HAFAS proxy returns no ticket prices. Candidates: ÖBB Scotty API, VAO, scraping ÖBB.at. Should be resolved before any public release — accurate pricing is core to the value proposition. | 🟠 High | M (4-6h) | ⬜ Todo | Pre-release | Elevated to High priority — this directly affects the accuracy of the app's core feature. See ADR #9.
— | Enhancement | More prefetched route prices | Add Graz, Salzburg, Innsbruck, Linz routes to ROUTE_PRICES in TripRouteFields.tsx. Currently only Villach routes. | 🔵 Low | XS (1h) | ⬜ Todo | Any | Quick win for Austria-wide usability pending proper pricing API
41 | UX | Empty states — Stats & Quests screens | New users (post #37 fix) land on Stats with empty/broken charts and Quests with all progress at 0. Both screens need proper empty state UI. | 🔴 Critical | S (2-4h) | ✅ Done | S13 | Stats: replace chart with illustration + CTA. Quests: show locked state with Add a trip to start earning XP prompt. · Completed S13 — Stats: full empty state replacing data sections. Quests: info banner. · Completed S13 — Stats: full empty state replacing data sections. Quests: info banner.
42 | UX | Manual date/time for trips | Users can only log trips at the current moment. No way to backfill yesterday's commute. A date/time picker on the Add Trip modal is needed for real-world usage. | 🟠 High | S (2-4h) | ✅ Done | S14 | Add DateTimePicker (expo-datetime-picker or RN DateTimePicker) to QuickAddTripModal. Default to now, allow past dates. · Completed S14 — Native DateTimePicker in both modals; iOS spinner+Done, Android dialog; single Date state
43 | Gamification | Streak system | Track consecutive days the user logs at least one trip. Display streak on UserLevelCard. Streak loss is a powerful retention mechanic (loss aversion). Fits thesis well. | 🟠 High | M (4-8h) | ⬜ Todo | Any | AsyncStorage key @currentStreak + @lastTripDate. Streak breaks if no trip logged by midnight. Consider streak freeze item as future extension.
44 | Onboarding | Onboarding rework package | Full onboarding overhaul before production: (1) new slide content + real images, (2) personalization step — set name + KlimaTicket type inline so users skip empty profile, (3) 'Add your first trip' prompt on completion. Package with PP3 (onboarding images). | 🟠 High | L (1-2d) | ⬜ Todo | Pre-launch | Supersedes PP3. Low current priority but must ship before production. Personalization step reduces time-to-value significantly.
45 | UX | Haptic feedback | Add haptic feedback on: trip add confirmation, XP toast, quest claim, level-up, slide-to-delete confirm. Quick win for perceived quality. | 🟡 Medium | XS (1h) | ⬜ Todo | Any | Use expo-haptics. Haptics.impactAsync(ImpactFeedbackStyle.Medium) for most; Heavy for level-up.
46 | UX | Trip list search and filter | Once users have 30+ trips the flat list becomes unwieldy. Add search by origin/destination and filter by transport type and/or date range. | 🟡 Medium | M (4-8h) | ⬜ Todo | Any | Filter bar above trip list in user.tsx. Client-side filtering on trips array — no API needed.
47 | Feature | Recurring trip / one-tap repeat | Allow users to repeat a previous trip with one tap — pre-fills all fields from the last matching trip. Reduces friction for daily commuters. | 🔵 Low | S (2-4h) | ⬜ Todo | Any | Could surface as a 'Repeat' button in TripDetailModal or as a quick-action in the favorites section.
48 | Feature | Push notifications | Streak-at-risk reminder (evening if no trip logged), daily quest expiry warning, weekly quest reset notification. | 🔵 Low | M (4-8h) | ⬜ Todo | Any | Requires expo-notifications + user permission prompt. Schedule local notifications — no backend needed for streak/quest reminders.
49 | Feature | Shareable achievement cards | When a user unlocks an achievement, offer a screenshot-friendly share card (achievement name, icon, app branding). Social loop and organic marketing. | 🔵 Low | S (2-4h) | ⬜ Todo | Any | Use expo-sharing + react-native-view-shot to capture the card as an image. Trigger from achievement claim.
50 | Tech Debt | Clean up stale XP seeding comment in user.tsx | Comment references ensuring 10 hardcoded dummy trips grant XP on fresh installs — no longer true after #37 fix. | 🔵 Low | XS (5m) | ⬜ Todo | Any | One-line comment update in the XP init useEffect block in user.tsx.
51 | UX | Offline / API error indicator | When ÖBB API is unreachable, connection search fails silently. Show a small inline 'Offline — manual entry only' notice in QuickAddTripModal when API calls fail. | 🔵 Low | XS (1h) | ⬜ Todo | Any | Catch fetch errors in oebbApi.ts and surface via a state flag in QuickAddTripModal. No retry logic needed.
PRE-PRODUCTION CHECKLIST
# | Category | Task | Description | Priority | Effort | Status | Target | Notes
PP1 | Pre-Prod | Re-enable email confirmation | Supabase email confirmation currently disabled for dev convenience. HARD BLOCKER — must be enabled before any real users can register. | 🔴 Critical | XS (5m) | ⬜ Todo | Pre-launch | Supabase dashboard → Authentication → Email → Enable confirmations
PP2 | Pre-Prod | Resolve Pricing API (see backlog) | The macistry.com HAFAS proxy returns no ticket prices. Without accurate pricing, the cost autofill gives wrong break-even calculations for many routes. | 🟠 High | M (4-6h) | ⬜ Todo | Pre-launch | Cross-listed from backlog. Elevated to pre-prod because pricing accuracy is the app's core claim.
PP3 | Pre-Prod | Add onboarding images | onboard1.png, onboard2.png, loginbg.png missing from assets/images/. Metro bundler fails without them — app cannot be built. | 🟡 Medium | S (design) | ⬜ Todo | Pre-launch | Slide 1: ROI annotated map. Slide 2: full KlimaTicket coverage map. loginbg: plain Austrian map.
PP4 | Pre-Prod | App Store assets & metadata | App icon, splash, description, screenshots required for iOS/Android submission. ASO keywords for Austrian market. | 🟡 Medium | M (1d) | ⬜ Todo | Pre-launch | EAS build + submission. Consider App Store Optimisation for 'KlimaTicket' and 'Öffi' search terms.
PP5 | Pre-Prod | Final regression pass + EAS build | Full device test on both iOS and Android before submission. Focus areas: auth flow, trip CRUD, quest rotation, delete all trips, KlimaTicket cost impact on stats. | 🟡 Medium | S (2-4h) | ⬜ Todo | Pre-launch | Test on physical devices not just simulator. Verify Supabase session persistence across app restarts.
COMPLETED — Archive (read-only reference)
# | Category | Task | Description | Priority | Effort | Status | Target | Notes
1 | Bug Fix | ÖBB Distance Fix | summariseJourney() 0m bug → 0 XP trips. haversine×1.25 fallback. | 🔴 Critical | S | ✅ Done | S7 | Completed S7
2 | Feature | Quests / Tasks Page | Daily/weekly/milestone quest pools, rotation, XP claim. | 🟠 High | L | ✅ Done | S8 | Completed S8
3 | Feature | Achievements / Badges | 19 achievements × 5 categories, computeStreak, computeSavedVsCar. | 🟠 High | M | ✅ Done | S8 | Completed S8
4 | Feature | Stats & Visualisations | app/stats.tsx — 4 stat cards, WeeklyBarChart, transport mix, top routes. | 🟠 High | L | ✅ Done | S10 | Completed S10
5 | Feature | CO2 Savings Display | CO2 saved card (0.16 kg/km); long-press tooltip with methodology. | 🟡 Medium | S | ✅ Done | S10 | Completed S10
6 | Feature | Trip Statistics Summary | Transport Mix + Top Routes + avg cost/trip. | 🟡 Medium | S | ✅ Done | S10 | Completed S10
9 | Tech Debt | Memoize computeFavorites | useMemo([trips]) in user.tsx | 🔵 Low | XS | ✅ Done | S11 | Completed S11
10 | Tech Debt | Centralise transport constants | constants/transport.ts — TRANSPORT_COLOR + transportIcon() | 🔵 Low | XS | ✅ Done | S11 | Completed S11
12 | Tech Debt | Debounce ÖBB search | 400ms debounce via searchDebounceRef in QuickAddTripModal | 🔵 Low | XS | ✅ Done | S11 | Completed S11
16 | Bug Fix | Price autofill mount fix | useRef(false) guard prevents autofill on modal open. | Medium | XS | ✅ Done | S7 | Completed S7
17 | UI | QuickAdd dark theme | Full dark theme matching TripDetailModal edit mode. | Medium | S | ✅ Done | S7 | Completed S7
18 | UX | Connection description autofill | Selecting connection fills 'Origin → Dest · HH:MM · TrainName'. | Low | XS | ✅ Done | S7 | Completed S7
19 | UX | Transport type default empty | Forces explicit selection; autofills on connection select. | Low | XS | ✅ Done | S7 | Completed S7
25 | Tech Debt | Memoize recentPlaces | useMemo([trips]) in user.tsx | 🔵 Low | XS | ✅ Done | S11 | Completed S11
26 | Tech Debt | Fix floating checkMainQuest promise | await added in handleFavoritePress + handleQuickAddSubmit | 🟡 Medium | XS | ✅ Done | S11 | Completed S11
27 | Tech Debt | Remove getTripById dead code | Removed from services/tripStorage.ts | 🔵 Low | XS | ✅ Done | S11 | Completed S11
28 | Tech Debt | Remove light theme TripRouteFields | theme prop + light styles removed; dark theme only. | 🔵 Low | XS | ✅ Done | S11 | Completed S11
29 | Tech Debt | Merge screenStyles into _user_styles.tsx | root style moved; screenStyles removed from user.tsx | 🔵 Low | XS | ✅ Done | S11 | Completed S11
30 | Tech Debt | Hoist typeIcon() → transportIcon() | Moved to constants/transport.ts as transportIcon() | 🔵 Low | XS | ✅ Done | S11 | Completed S11
31 | Tech Debt | eslint-disable TripRouteFields useEffect | Comment documents intentional mount guard pattern | 🔵 Low | XS | ✅ Done | S11 | Completed S11
33 | Bug Fix | Rename user_styles → _user_styles.tsx | Expo Router route warning fixed by _ prefix | 🟡 Medium | XS | ✅ Done | S12 | Completed S12
34 | Feature | KlimaTicket presets overhaul | TICKET_GROUPS: 6 nationwide + 20 regional, real 2026 prices. | 🟠 High | S | ✅ Done | S12 | Completed S12
35 | Feature | Delete All Trips slide-to-confirm | SlideToDelete: RNGH Pan + absolute overlay + saveTrips([]) | 🟠 High | M | ✅ Done | S12 | Completed S12

## ⚠️ Gotchas
⚠️ Gotchas, Decisions & Hard-Won Lessons
Non-obvious platform constraints and rules that must be followed. Check this sheet before touching any listed area. Primary source for 'Limitations' thesis sections.
Area | The Rule / Decision | Why — full context | What breaks if ignored | Session | Severity | Thesis angle
Icons in Modals | NEVER use IconSymbol (SF Symbols) in any Modal or overlay. Use MaterialIcons only. | SF Symbols are rendered by iOS's symbol system, which is unavailable inside React Native Modal's isolated native view hierarchy. Icons silently render as invisible — no crash, no warning. | All icons in modals are blank on iOS. No error message, no stack trace — invisible failure. | S3 | 🔴 Critical | Platform limitations
RNGH in RN Modal | RNGH gesture handlers do NOT work inside React Native Modal. Use absolute View overlay instead. | React Native Modal creates a separate native view hierarchy. RNGH cannot intercept events across this boundary. Pan, LongPress, and all other RNGH gestures fire no callbacks inside Modal on iOS. | Gesture callbacks never fire. No error. Silently broken interaction — extremely hard to diagnose. | S12 | 🔴 Critical | Platform limitations
Delete All Trips — correct method | Must call saveTrips([]) on @travelapp_trips. Never AsyncStorage.removeItem on any key. | removeItem(@trips) silently does nothing (wrong key). removeItem(@travelapp_trips) causes loadTrips() to hit the initialTrips fallback on next load, making it appear the delete had no effect. | Trips appear undeleted — demo data reappears on next app load. No error, maximum user confusion. | S12 | 🔴 Critical | Data integrity
Expo Router file naming | Files in app/ prefixed with _ are ignored by the router. Style/utility files MUST start with _. | Expo Router v6 treats every file in app/ as a potential route and emits a missing-default-export warning for files without a component export. The _ prefix opts a file out of routing entirely. | Console warning: 'Route file missing default export'. Non-fatal but pollutes logs and confuses tooling. | S12 | 🟡 Medium | Framework conventions
services/ and types/ location | Keep services/ and types/ OUTSIDE the app/ directory. | Expo Router processes all files under app/ as routes. tripStorage.ts or trip.ts inside app/ would create phantom routes (/tripStorage, /trip) with no component. | Phantom routes in the router. Missing default export warnings. Risk of navigation to blank screens. | S1 | 🟠 High | Project architecture
AsyncStorage XP storage | XP is a string in AsyncStorage. Always parseInt(). Seed from trips if result is NaN. | AsyncStorage is string-only. Old app versions stored the literal string 'NaN'. parseInt('NaN') returns NaN not 0. Guard: if isNaN(xp) → re-seed from all trips. | User sees level 0 and empty XP bar despite having many trips logged. | S3 | 🟡 Medium | Data persistence
Palette — no hardcoded hex | Only #fff is permitted as hardcoded hex. All colours must come from Palette or constants/transport.ts. | 9-colour Palette in constants/Colors.ts is the single source of truth. Scattered hex values make global colour changes impractical and create visual inconsistencies. | Visual inconsistencies. Colour changes require grep across all files rather than one edit. | S1 | 🔵 Info | Design system
react-native-gifted-charts | Do NOT add chart libraries without testing Metro bundler compatibility in Expo managed workflow. | gifted-charts caused an unresolvable Metro bundler resolution error after install in S10. The Expo managed workflow has stricter Metro constraints than bare React Native. | Metro fails to start. No clear error — requires tracing bundler resolution logs. | S10 | 🟡 Medium | Dependency management
Reanimated v4 peer dep | react-native-worklets must be explicitly installed alongside react-native-reanimated v4. | Reanimated v4 split its worklet runtime into a separate package not automatically installed transitively. | App crashes at bundle time: 'Cannot resolve react-native-worklets'. No animations work. | Pre-S | 🟠 High | Dependency management
Supabase ws shim | The 'ws' package must be shimmed to empty in metro.config.js for Supabase to work. | Supabase Realtime depends on 'ws' which requires Node.js 'stream'. React Native has no 'stream'. Shim makes Supabase fall back to native WebSocket. | Bundle error: 'Unable to resolve module stream'. App fails to start. | Pre-S | 🟠 High | Platform compatibility
GestureHandlerRootView | Must wrap the ENTIRE app in _layout.tsx, not individual screens. | RNGH requires a single GestureHandlerRootView at the root to set up the native gesture hierarchy. Per-screen wrapping means gestures on other screens may lose priority negotiation. | Hold gestures on Favorites may fail silently on screens without individual wrapping. | S2 | 🟡 Medium | Gesture architecture
checkMainQuest — must await | Always call checkMainQuest() with await in handleFavoritePress and handleQuickAddSubmit. | checkMainQuest is async (reads AsyncStorage). Without await, errors are silently swallowed and the Main Quest celebration may not fire on slow devices. | Main Quest overlay never appears or appears inconsistently. No error surfaced. | S11 | 🟡 Medium | Async error handling
CO2 factor — needs citation | The 0.16 kg/km CO₂ factor in stats.tsx needs a citable source before thesis submission. | Currently derived as car average (0.21) minus public transport (0.05) kg/km without citing a primary source. For thesis and for user trust, this must reference Austrian Federal Environment Agency or comparable official data. | Academically unciteable in thesis. Potential user trust issue if questioned. | S10 | 🟡 Medium | Academic rigour / Data sources
CRLF files + Edit tool string matching | Files with Windows CRLF line endings must be fully rewritten — never use targeted Edit. | The Edit tool matches exact byte strings. CRLF (\r\n) line endings cause every match to fail silently or partially, leading to cascading TS errors or phantom rewrites. Diagnosed via cat -A; the only reliable fix is a full Write of the affected file. | Edit silently fails, file unchanged; downstream TS errors if a partial write occurs. | S14 | 🟠 High | Platform limitations / DX

## 🎯 Milestones
🎯 Milestones & Projections
6 of 7 milestones complete · M7 Production Ready target: 2026-04-12
MILESTONE TRACKER
ID | Milestone | Target | Status | Key Deliverables | Blockers | Sessions
M1 | Core MVP | 2026-03-14 | ✅ Complete (100%) | Trip CRUD, AsyncStorage, FinancialOverview SVG donut, transport accent bars, 10 seed trips | — | S1–S2
M2 | Auth & Onboarding | 2026-03-15 | ✅ Complete (100%) | Supabase auth, dark Login/Register, 3-slide onboarding pager, animated splash screen | — | S4
M3 | Full Trip Lifecycle | 2026-03-15 | ✅ Complete (100%) | TripDetailModal (view/edit/delete), XP delta on edit, XPToast, LevelUpOverlay, empty state, profile, KlimaTicket setting | — | S3, S5
M4 | UX Polish | 2026-03-15 | ✅ Complete (100%) | Shared TripRouteFields, price autofill, recent places suggestions, swap button, distance estimator | — | S6
M5 | Gamification 2.0 | 2026-03-15 | ✅ Complete (100%) | Quest system (daily/weekly/milestone pools), 19 achievements × 5 categories, Quests & Achievements screen, Main Quest overlay (2000 XP) | — | S8
M6 | Stats & Insights | 2026-03-16 | ✅ Complete (100%) | Stats screen: 4 stat cards, WeeklyBarChart, Transport Mix, Top Routes, CO₂ with long-press tooltip | — | S10
M7 | Production Ready | 2026-04-12 | ⬜ Planned (0%) | Bugs #36/#37 fixed, pricing API resolved, email confirm re-enabled, onboarding images, App Store assets, final QA + EAS build | Image assets (design work), Pricing API research, App Store developer account | S13+

## ✅ Feature Registry
✅ Complete Feature Registry — All 35 Shipped Features
Every shipped feature with session delivered, primary files, theory reference, and modification history. Use for methodology appendix.
# | Feature | Category | Session | Also Modified In | Primary Files | Description | XP Impact | Theory Reference | Thesis Tag
1 | Trip CRUD | Core | S1 | — | tripStorage.ts, user.tsx | Add, load, save trips to AsyncStorage. Key: @travelapp_trips | — | — | Data Architecture
2 | 10 Dummy Seed Trips | Core | S1 | — | tripStorage.ts | Fallback initial data — PRE-PROD BUG #37 (change to []) | Seeds XP | — | Data Architecture
3 | FinancialOverview Card | UI | S1 | S5, S6, S9 | FinancialOverview.tsx | Collapsible savings card with SVG donut; klimaTicketCost from profile; donut tappable → /stats | — | — | Interface Design
4 | Transport Accent Bars | UI | S1 | S11 | user.tsx, _user_styles.tsx | Colour-coded left border on trip cards; colours centralised to constants/transport.ts in S11 | — | — | Interface Design
5 | XP / Level System | Gamification | S2 | S3, S5 | levelSystem.ts, user.tsx | getXPForTrip (base+distance capped 50km+multiplier), calculateLevel, getLevelTitle | Core | Deterding et al. (2011) — points-and-levels gamification framework; Intrinsic motivation (Deci & Ryan SDT) | Gamification Theory
6 | UserLevelCard | UI | S2 | S5, S8 | UserLevelCard.tsx | Animated XP progress bar; level title; quests entry point added S8 | Display | Goal gradient effect (Hull 1932); Progress principle (Amabile & Kramer 2011) | Interface Design
7 | Favorites Hold-to-Add | UX | S2 | S11 | user.tsx, _user_styles.tsx | RNGH LongPress 1000ms fill animation; memoized in S11 | Yes | Flow theory (Csikszentmihalyi 1990); Engagement through challenge; Operant conditioning (Skinner) | UX Design
8 | Show All / Show Less Toggle | UI | S2 | — | user.tsx | Recent Trips: defaults 5; expand/collapse all | — | — | Interface Design
9 | TripDetailModal (view+delete) | Feature | S3 | S5 | TripDetailModal.tsx | Tap trip → details; delete with confirm overlay; edit mode added S5 | Delete: −XP | Immediate feedback principle (Hattie & Timperley 2007); Operant conditioning | Feature Design
10 | XP Seeding Fix | Bug Fix | S3 | — | user.tsx, tripStorage.ts | Seeds XP from trips if stored value is NaN or missing | Fixes XP | Data integrity / error handling pattern — not gamification theory | Bug Analysis
11 | Logout Button | Auth | S3 | — | user.tsx | Red-bordered; signOut(); routes to /onboarding | — | — | Auth Architecture
12 | Safe-Area + UX Overhaul | UX | S3 | — | user.tsx, _user_styles.tsx | paddingTop:52, loading spinner, section icons, scroll padding | — | — | UX Design
13 | Supabase Auth | Auth | S4 | S4 (register) | supabase.ts, LoginForm, RegisterForm | Real email/password auth; AsyncStorage session persistence | — | — | Auth Architecture
14 | Dark Login Screen | UI | S4 | — | login.tsx, LoginForm.tsx | ImageBackground + LinearGradient overlay; Palette dark design | — | — | Interface Design
15 | Dark Register Screen | UI | S4 | — | register.tsx, RegisterForm.tsx | Matches login; success state before redirect | — | — | Interface Design
16 | 3-Slide Onboarding | Onboarding | S4 | — | onboarding.tsx | FlatList pagingEnabled pager; tappable dots; CTA only on last slide | — | — | FRE Design
17 | Animated Splash Screen | UX | S4 | — | index.tsx | Reanimated scale+fade 2s; Supabase session check before routing | — | First impressions and onboarding UX (Spool 2009); Perceived performance | UX Design
18 | Trip Editing | Feature | S5 | — | TripDetailModal.tsx | mode:'view'¦'edit'; pre-filled form; XP delta on save (floored at 0) | XP delta | Trip editing: data integrity + XP fairness — not gamification theory | Feature Design
19 | XPToast | Gamification | S5 | — | XPToast.tsx | Floating '+N XP' badge; Reanimated spring+float ~1.2s | Display | Immediate reinforcement (Skinner 1938); Micro-feedback UX (Saffer 2013) | Gamification Theory
20 | LevelUpOverlay | Gamification | S5 | — | LevelUpOverlay.tsx | Full-screen celebration; spring-in card; auto-dismiss ~2.8s | Display | Level-up ceremony: milestone acknowledgement in SDT; Celebration mechanics (Zichermann & Cunningham 2011) | Gamification Theory
21 | Empty State | UX | S5 | — | user.tsx | Icon + message + CTA when no trips logged | — | — | UX Design
22 | KlimaTicket Cost Setting | Settings | S5 | S12 | profile.tsx | Dropdown presets persisted; overhaul to real 2026 prices in S12 | Affects savings | Goal-setting theory (Locke & Latham 1990); User-defined targets | User Configuration
23 | User Profile Screen | Feature | S5 | S8, S12 | profile.tsx | Avatar, name, KlimaTicket picker, danger zone; achievement+stats buttons added | — | Self-representation / avatar theory (Yee & Bailenson 2007); User agency | Feature Design
24 | TripRouteFields (shared) | Refactor | S6 | S7, S11 | TripRouteFields.tsx | Shared route component; dark theme only after S11 | — | — | Software Quality
25 | Price Autofill | UX | S6 | — | TripRouteFields.tsx | ROUTE_PRICES + TRANSPORT_FLAT_PRICES; useRef(false) mount guard | — | — | UX Design
26 | Suggestions Dropdown | UX | S6 | S11 | TripRouteFields.tsx | recentPlaces by frequency; useMemo added S11 | — | — | UX Design
27 | Swap Origin/Destination | UX | S6 | — | TripRouteFields.tsx | Single tap reverses origin and destination | — | — | UX Design
28 | Distance Estimator | Feature | S6 | — | TripRouteFields.tsx, oebbApi.ts | Estimate button; haversine × 1.25 detour factor | Affects XP | Distance as effort proxy; Eco-feedback systems (Froehlich et al. 2010) | Feature Design
29 | ÖBB Distance Fix | Bug Fix | S7 | — | oebbApi.ts | summariseJourney haversine fallback when HAFAS returns 0m distance | Fixes 0 XP | — | Bug Analysis
30 | Price Autofill Mount Fix | Bug Fix | S7 | — | TripRouteFields.tsx | useRef(false) guard prevents autofill overwriting user input on open | — | — | Bug Analysis
31 | QuickAdd Dark Theme | UI | S7 | — | QuickAddTripModal.tsx | Full dark theme matching TripDetailModal edit mode | — | — | Interface Design
32 | Connection Description Autofill | UX | S7 | — | QuickAddTripModal.tsx | Selecting ÖBB connection fills 'Origin → Dest · HH:MM · Train' | — | — | UX Design
33 | Transport Default Empty | UX | S7 | — | QuickAddTripModal.tsx | Forces explicit user selection; autofills from connection select | — | — | UX Design
34 | Quest System | Gamification | S8 | S11 | utils/questSystem.ts | Daily(8)/weekly(8)/milestone(9) pools; date-keyed rotation; await fix S11 | Quest XP | Quest / challenge mechanics (Werbach & Hunter 2012); Intrinsic motivation | Gamification Theory
35 | Achievement System | Gamification | S8 | — | utils/achievementSystem.ts | 19 achievements × 5 categories; computeStreak; computeSavedVsCar | — | Achievement systems (Hamari & Eranti 2011); Badge mechanics; Social comparison | Gamification Theory
36 | Quests & Achievements Screen | Feature | S8 | — | app/quests.tsx | Segmented tabs; QuestCard; AchievementCard; XP claim; deep-link ?tab= | XP on claim | Quest screen UX — see quest system theory above | Feature Design
37 | Main Quest Featured Card | Gamification | S8 | — | app/quests.tsx | Red-border card; €X/€Y progress; CLAIM 2000 XP | 2000 XP | Variable reward schedule (Skinner 1938); Intermittent reinforcement; Return visit motivation | Gamification Theory
38 | MainQuestOverlay | Gamification | S8 | — | MainQuestOverlay.tsx | 6 floating stars; spring-in card; one-time @mainQuestCelebrated flag | Display | Main Quest as narrative arc (Montola et al. 2009); Climax moment in gamification | Gamification Theory
39 | Main Quest Break-Even Detection | Feature | S8 | — | app/(tabs)/user.tsx | checkMainQuest() after every trip add; compares savings to klimaTicketCost | Triggers 2000 XP | Break-even as goal clarity; Milestone acknowledgement in SDT; Commitment device theory | Feature Design
40 | UserLevelCard Quests Link | UI | S8 | — | UserLevelCard.tsx | Bottom row with chevron → /quests | — | — | Interface Design
41 | Profile Achievements Button | UX | S8 | — | profile.tsx | Deep-links to /quests?tab=achievements | — | — | UX Design
42 | Stats & Insights Screen | Stats | S10 | — | app/stats.tsx | 4 stat cards, CO₂ tooltip, KlimaTicket progress, WeeklyBarChart, Transport Mix, Top Routes | — | Eco-feedback systems (Froehlich et al. 2010); CO₂ literacy; Behaviour change through information (Thaler & Sunstein 2008) | Data Visualisation
43 | Stats Entry — Donut | UI | S10 | — | FinancialOverview.tsx | SVG donut → TouchableOpacity → /stats via onStatsPress | — | — | Interface Design
44 | Stats Entry — Profile | UX | S10 | — | profile.tsx | 'Stats & Insights' button → /stats | — | — | UX Design
45 | KlimaTicket Presets Overhaul | Settings | S12 | — | profile.tsx | TICKET_GROUPS: 6 nationwide + 20 regional, real 2026 Austrian prices | Affects savings | User-configured incentive design; Nudge theory (Thaler & Sunstein 2008); Personalisation in gamification | User Configuration
46 | Delete All Trips Slide | Feature | S12 | — | profile.tsx | SlideToDelete: RNGH Pan + absolute overlay + saveTrips([]). NOT RN Modal. | Resets XP | — | Feature Design
47 | PM Updater Script | PM | S8 | S12 (v3 struct) | pm_updater.py | PMUpdater class; 14 methods; idempotent; ~2min session update vs ~15min manual | — | — | Development Process