## 📊 Dashboard
🚂 KlimaChallenge — TravelApp ¦ Project Management Dashboard
Session 12 Complete ¦ Date: 2026-03-16 ¦ Platform: React Native / Expo
KEY METRICS
Sessions Completed |  | Features Shipped |  | Backlog Items Left |  | Tech Debt Items | Pre-Prod Blockers
12 |  | 35 |  | 5 |  | 0 | 3
11 |  | 33 |  | 5
SESSION TIMELINE
Session | Date | Status | Key Deliverables | Files Changed | Notes
S1 | 2026-03-14 | ✅ Done | Initial app scaffold, Expo Router, Tab nav, AsyncStorage trip CRUD, 10 dummy trips, FinancialOverview savings card | app/_layout, index, (tabs)/user, services/tripStorage | Foundation sprint
S2 | 2026-03-14 | ✅ Done | Favorites hold-to-add (RNGH LongPress), XP/level system (utils/levelSystem), UserLevelCard, transport accent bars, Show all/less toggle | user.tsx, user_styles, levelSystem.ts, UserLevelCard | RNGH chosen after 5 failed approaches
S3 | 2026-03-15 | ✅ Done | TripDetailModal (view+delete), XP seeding fix, Logout (Supabase signOut), User page safe-area overhaul | TripDetailModal, user.tsx, tripStorage, register.tsx | MaterialIcons in modals — SF Symbols unreliable on iOS
S4 | 2026-03-15 | ✅ Done | Real Supabase auth (signIn/signUp), lib/supabase.ts singleton, dark Login+Register screens, Onboarding 3-slide pager, animated Splash | login, register, onboarding, index, supabase.ts, LoginForm, RegisterForm | Email confirm disabled for dev
S5 | 2026-03-15 | ✅ Done | Trip editing in TripDetailModal, XPToast floating badge, LevelUpOverlay celebration, Empty state, KlimaTicket cost setting, User Profile screen, Level-up animation | TripDetailModal, user.tsx, XPToast, LevelUpOverlay, profile.tsx, levelSystem.ts | 9 features in one session
S6 | 2026-03-15 | ✅ Done | TripRouteFields shared component, price autofill (ROUTE_PRICES + TRANSPORT_FLAT_PRICES), suggestions dropdown, swap button, distance estimator (haversine×1.25) | TripRouteFields, oebbApi.ts, QuickAddTripModal, TripDetailModal | Reduced code duplication between Add and Edit flows
S7 | 2026-03-15 | Done | OBB distance fix (haversine fallback), QuickAdd dark theme, price mount fix, connection description autofill, transport default empty, layout improvements, PM Excel | oebbApi.ts, TripRouteFields.tsx, QuickAddTripModal.tsx, KlimaChallenge_PM.xlsx | 7 features; QuickAdd fully reworked to dark theme
S8 | 2026-03-15 | ✅ Done | Quest System (daily/weekly/milestone pools, rotation, AsyncStorage), Achievement System (19 achievements, 5 categories), Quests & Achievements screen (segmented tabs, XP claim, deep-link), Main Quest featured card, MainQuestOverlay (Reanimated celebration), user.tsx checkMainQuest, UserLevelCard quests link, profile View Achievements button | utils/questSystem.ts (new), utils/achievementSystem.ts (new), app/quests.tsx (new), components/ui/MainQuestOverlay.tsx (new), app/(tabs)/user.tsx, components/ui/UserLevelCard.tsx, app/profile.tsx | 8 features; full gamification loop complete
S9 | 2026-03-16 | ✅ Done | Stats & Insights screen (4 stat cards, KlimaTicket progress bar, WeeklyBarChart custom view, Transport Mix, Top Routes, CO2 long-press tooltip), FinancialOverview donut tappable -> /stats, profile Stats & Insights button -> /stats | app/stats.tsx (new), components/ui/FinancialOverview.tsx, app/profile.tsx | 3 features; no chart library (gifted-charts removed - Metro bundler bug); custom View-based bars
S11 | 2026-03-16 | ✅ Done | Tech debt sprint: 9 items cleared. Memory files added to git repo. | constants/transport.ts (new), user.tsx, stats.tsx, TripRouteFields.tsx, QuickAddTripModal.tsx, user_styles.tsx, tripStorage.ts, .claude/memory/ | All tech debt cleared. Transport colors centralised. useMemo, await fixes, dead code removed, light theme removed, debounce added.
S12 | 2026-03-16 | ✅ Done | KlimaTicket presets overhaul (6 nationwide + 20 regional, real 2026 prices). Delete All Trips with slide-to-confirm. Bug fixes: typeIcon crash, Expo Router route warning, RNGH-in-Modal, wrong AsyncStorage key. | profile.tsx, stats.tsx, app/(tabs)/user.tsx, app/(tabs)/_user_styles.tsx (renamed) | 3 compounding bugs in Delete All Trips: RNGH gestures dead in RN Modal (fixed with absolute overlay), runOnJS broken on web (fixed with .runOnJS(true)+setTimeout), wrong storage key @trips vs @travelapp_trips + initialTrips fallback (fixed with saveTrips([])).

## 📋 Backlog & Tasks
KlimaChallenge — Backlog & Task Board
Priority-ordered remaining work ¦ Updated 2026-03-16 ¦ Session 12 complete
# | Category | Task | Description | Priority | Effort | Status | Session Target | Notes
1 | Bug Fix | ÖBB Distance Fix | summariseJourney() returns no distance → trips log 0km and earn 0 XP. Extract distance from journey data. | 🔴 Critical | S (1-2h) | Done | S7 | Completed S7 - searchConnections returns {journeys,fromStation,toStation}; haversine x1.25 fallback when API returns 0m
2 | Feature | Quests / Tasks Page | Daily/weekly quests screen. Motivates regular app usage. Define quest types (streak, transport variety, distance milestones). | 🟠 High | L (1-2d) | Done | S8 | Completed S8 - daily/weekly/milestone quest pools, random rotation, AsyncStorage by date key, QuestCard/SectionHeader, XP claim with XPToast+LevelUpOverlay
3 | Feature | Achievements / Badges Tab | Unlockable achievements. e.g. '100km club', 'Train Master'. Show locked/unlocked state with progress. | 🟠 High | M (4-8h) | Done | S8 | Completed S8 - 19 achievements across 5 categories, AchievementCard, computeStreak/computeSavedVsCar helpers, shared screen with Quests via segmented control
4 | Feature | Stats & Visualisations Screen | Dedicated stats screen: trips/time bar chart, transport breakdown pie, total distance, avg cost, most used route, CO2 savings. Link from profile. | 🟠 High | L (1-2d) | ✅ Done | S8-S9 | Completed S9 - app/stats.tsx; 4 stat cards; KlimaTicket progress bar; WeeklyBarChart (custom View, 8 ISO weeks); Transport Mix; Top Routes (top 5); CO2 factor 0.16 kg/km
5 | Feature | CO2 Savings Display | App is climate-focused but shows no carbon numbers. Add CO2 saved estimate (car vs PT). Could be in FinancialOverview or Stats screen. | 🟡 Medium | S (2-4h) | ✅ Done | S9 | Completed S9 - CO2 saved stat card (0.16 kg/km x distance); long-press tooltip with methodology
6 | Feature | Trip Statistics Summary | Surface avg cost, most used route, most common transport type. Data exists. Display in Stats screen. | 🟡 Medium | S (2-4h) | ✅ Done | S9 | Completed S9 - Transport Mix (horizontal bars, %) + Top Routes (ranked top 5) + avg cost/trip + total distance
7 | Research | Pricing API Research | Find public API for ÖBB / Austrian PT pricing. macistry HAFAS returns no ticket prices. Candidates: ÖBB Scotty API, VAO, scraping ÖBB.at. | 🟡 Medium | M (4-6h) | ⬜ Todo | S10 | Needed for accurate cost autofill
8 | Enhancement | More Prefetched Route Prices | Add Graz, Salzburg, Innsbruck, Linz routes to ROUTE_PRICES in TripRouteFields.tsx. Current: Villach↔Klagenfurt, Villach↔Wien only. | 🔵 Low | XS (1h) | ⬜ Todo | S10 | Quick win, improves Austria-wide usability
9 | Tech Debt | Memoize computeFavorites | Called on every render in user.tsx. Wrap in useMemo([trips]). | 🔵 Low | XS (30m) | ✅ Done | Any | useMemo([trips]) in user.tsx
10 | Tech Debt | Centralise Transport Constants | Transport color/type maps defined separately in user.tsx and QuickAddTripModal.tsx. Extract to shared constants file. | 🔵 Low | XS (1h) | ✅ Done | Any | constants/transport.ts — TRANSPORT_COLOR + transportIcon()
11 | Tech Debt | Normalise trip.date on Load | After AsyncStorage JSON roundtrip, trip.date is a string but treated as Date. Coerce to Date in loadTrips(). | 🟡 Medium | XS (30m) | ✅ Done | S7 | Already resolved - loadTrips() does date: new Date(trip.date) on parse. Closed S9 audit.
12 | Tech Debt | Debounce ÖBB Connection Search | No debounce on station search; user can fire multiple rapid requests. Add 300ms debounce. | 🔵 Low | XS (1h) | ✅ Done | Any | 400ms debounce via searchDebounceRef in QuickAddTripModal
13 | Pre-Prod | Re-enable Email Confirmation | Supabase email confirmation disabled for dev convenience. Must re-enable before production release. | 🔴 Critical | XS (5m) | ⬜ Todo | Pre-launch | BLOCKER for production
14 | Pre-Prod | Add Onboarding Images | Placeholder images needed: onboard1.png, onboard2.png, loginbg.png in assets/images/. | 🟡 Medium | S (2-4h) | ⬜ Todo | Pre-launch | Design/asset work
15 | Pre-Prod | App Store Assets & Metadata | Icon, splash, app name, description, screenshots for App Store / Play Store submission. | 🟡 Medium | M (1d) | ⬜ Todo | Pre-launch
16 | Bug Fix | Price Autofill Mount Fix | useRef(false) guard in TripRouteFields prevents autofill firing on modal open. Price only fills when user actively changes a field. | Medium | XS (1h) | Done | S7 | Completed S7 - prevents stale price overwrite on modal open
17 | UI | QuickAdd Dark Theme | QuickAddTripModal fully converted to dark theme matching TripDetailModal edit mode. Inputs, date/time/transport rows, connection list, date picker. | Medium | S (2-4h) | Done | S7 | Completed S7 - visually identical to edit modal
18 | UX | Connection Description Autofill | Selecting an OBB connection fills description as "Origin -> Dest HH:MM TrainName". Reduces manual entry. | Low | XS (1h) | Done | S7 | Completed S7
19 | UX | Transport Type Default Empty | QuickAdd transport defaults to empty; user must actively pick; dimmed placeholder; autofilled on connection select. | Low | XS (30m) | Done | S7 | Completed S7
20 | UI | QuickAdd Layout Improvements | Distance below price; fieldLabels for Connection/Ticket Price/Distance; euro prefix + km suffix; 20% margin reduction. | Low | S (2-4h) | Done | S7 | Completed S7
21 | PM | KlimaChallenge PM Excel | 5-sheet project management file: Dashboard, Backlog & Tasks, Milestones, Architecture, Feature Registry. | Low | S (2-4h) | Done | S7 | Completed S7
22 | Feature | Quest Rotation (daily/weekly) | Random selection of 3 from daily/weekly pool, stored in AsyncStorage by date key. Refreshes at midnight/Monday. | Medium | M (4-8h) | Done | S8 | Completed S8 - getClaimKey, timeUntilMidnight, daysUntilMonday helpers
23 | Feature | Main Quest Break-Even Detection + Overlay | Detects when user savings exceed klimaTicketCost; triggers one-time MainQuestOverlay with Reanimated animation. Flag stored in AsyncStorage. | High | M (4-8h) | Done | S8 | Completed S8 - checkMainQuest() in user.tsx; MAIN_QUEST_CELEBRATED_KEY flag
24 | Feature | Main Quest Featured Card | Prominent card at top of Quests tab showing Klima Ticket break-even progress (red progress bar, euro stats, CLAIM 2000 XP button). | High | S (2-4h) | Done | S8 | Completed S8 - MainQuestFeaturedCard component in quests.tsx
25 | Tech Debt | Memoize recentPlaces | recentPlaces IIFE computed inline on every render in user.tsx (same pattern as computeFavorites). Wrap in useMemo([trips]). | 🔵 Low | XS (30m) | ✅ Done | S10 | useMemo([trips]) in user.tsx
26 | Tech Debt | Fix Floating checkMainQuest Promise | checkMainQuest() called without await in handleFavoritePress and handleQuickAddSubmit. Errors silently swallowed. | 🟡 Medium | XS (15m) | ✅ Done | S10 | await added in handleFavoritePress + handleQuickAddSubmit
27 | Tech Debt | Remove getTripById Dead Code | getTripById() in tripStorage.ts is never called anywhere in the codebase. Dead code from old trip detail screen. | 🔵 Low | XS (5m) | ✅ Done | S10 | getTripById removed from tripStorage.ts
28 | Tech Debt | Verify / Remove Light Theme in TripRouteFields | TripRouteFields has full light-theme StyleSheet. QuickAdd was converted to dark (S7) — verify theme=light is unused; remove dead styles. | 🔵 Low | XS (30m) | ✅ Done | S10 | theme prop + light styles removed from TripRouteFields
29 | Tech Debt | Merge screenStyles into user_styles.tsx | user.tsx has a separate screenStyles StyleSheet with a single entry (root: flex 1). Should live in user_styles.tsx. | 🔵 Low | XS (5m) | ✅ Done | S10 | root style moved to user_styles.tsx; screenStyles removed
30 | Tech Debt | Hoist typeIcon() in stats.tsx | typeIcon() helper defined after the component that uses it in stats.tsx. Hoist above StatsScreen. | 🔵 Low | XS (5m) | ✅ Done | S10 | typeIcon() moved to constants/transport.ts as transportIcon()
31 | Tech Debt | Add eslint-disable to TripRouteFields useEffect | useEffect intentionally omits cost/onCostChange from deps (mount guard pattern). Add eslint-disable-next-line comment to document intent. | 🔵 Low | XS (5m) | ✅ Done | S10 | eslint-disable comment added above useEffect mount guard
32 | PM | PM Updater Script | Persistent Python helper (pm_updater.py) with PMUpdater class to update KlimaChallenge_PM.xlsx. Replaces one-off scripts written each session. Methods: add_session_row, mark_backlog_done, add_backlog_item, add_feature, update_milestone, add_velocity_row, update_sprint_plan, add_arch_session. | 🔵 Low | S (1-2h) | ✅ Done | S10 | Completed S10 - PMUpdater class with 14 methods; dynamic row-finding; idempotent (skip if already exists); __main__ template for Claude to fill each session.
33 | Bug Fix | Rename user_styles.tsx to _user_styles.tsx | Expo Router treated user_styles.tsx as a route — missing default export warning | 🟡 Medium | XS (15m) | ✅ Done | S12 | Prefixed with _ (Expo Router ignores underscore files). Updated import in user.tsx.
34 | Feature | KlimaTicket presets overhaul | Replace placeholder presets with real 2026 Austrian KlimaTicket prices grouped by Nationwide/Regional | 🟠 High | S (2-4h) | ✅ Done | S12 | TICKET_GROUPS: 6 nationwide + 20 regional variants. Grouped dropdown with section headers and description field.
35 | Feature | Delete All Trips with slide-to-confirm | Danger Zone in profile — slide gesture confirmation before wiping all trips and XP | 🟠 High | M (4-8h) | ✅ Done | S12 | SlideToDelete: RNGH Gesture.Pan().runOnJS(true) + absolute overlay (NOT RN Modal). saveTrips([]) to clear. useFocusEffect reloads trips+XP on return.

## 🎯 Milestones
KlimaChallenge — Milestones & Projections
Based on ~1 session/day velocity ¦ ~5-8 features per session
MILESTONE TRACKER
Milestone | Target Date | Status | Completion % | Key Deliverables | Blockers | Notes
M1: Core MVP | 2026-03-14 | ✅ Complete | 100% | Trip CRUD, AsyncStorage, FinancialOverview, XP/Level, Favorites | None | Sessions 1-2
M2: Auth & Onboarding | 2026-03-15 | ✅ Complete | 100% | Supabase auth, Login/Register dark screens, 3-slide onboarding, animated splash | None | Session 4
M3: Full Trip Lifecycle | 2026-03-15 | ✅ Complete | 100% | Trip edit/delete, XP toast, level-up overlay, empty state, user profile, KlimaTicket setting | None | Sessions 3, 5
M4: UX Polish | 2026-03-15 | ✅ Complete | 100% | Shared TripRouteFields, price autofill, suggestions, swap, distance estimator | None | Session 6
M5: Gamification 2.0 | 2026-03-22 | ✅ Complete | 100% | Quest System (daily/weekly/milestone pools), Achievement System (19 achievements), Quests & Achievements screen, Main Quest featured card + overlay, ÖBB distance fix, CO2 savings (via computeSavedVsCar) | ÖBB distance data extraction | Sessions 7-8; fully complete
M6: Stats & Insights | 2026-03-16 | ✅ Complete | 100% | Stats screen with charts, CO2 display, trip statistics, transport mix, top routes | None | Sessions 8-9; complete end of S9
M7: Production Ready | 2026-04-12 | ⬜ Planned | 0% | Email confirm re-enabled, onboarding images, App Store assets, final QA pass | Asset creation needed | Sessions 10+
FEATURE VELOCITY (Features Shipped Per Session)
Session | Date | Features Shipped | Cumulative Total | Tech Debt Items | Category Mix
S1 | Mar 14 | 4 | 4 | 0 | Infra, CRUD
S2 | Mar 14 | 3 | 7 | 0 | UX, Gamification
S3 | Mar 15 | 4 | 11 | 0 | Bug Fix, UX
S4 | Mar 15 | 3 | 14 | 0 | Auth, Onboarding
S5 | Mar 15 | 9 | 23 | 0 | Features, UX, Settings
S6 | Mar 15 | 5 | 28 | 0 | Refactor, UX
S7 | Mar 15 | 7 | 35 | 0 | Bug Fix, UI, UX, PM
S8 | Mar 15 | 8 | 43 | 0 | Gamification, Quests, Achievements
S9 | Mar 16 | 3 | 46 | 0 | Stats & Insights
SESSION / SPRINT PLAN PROJECTION
Session | Target Date | Priority Focus | Planned Items | Est. Effort | Risk | Confidence
S7 | 2026-03-15 | Bug Fix + QuickAdd Overhaul | OBB distance fix, QuickAdd dark theme, price mount fix, connection/transport autofill, layout improvements, PM Excel | Medium | Done | Completed - 7 features
S8 | 2026-03-15 | Quests + Achievements | Full quests UI, achievements/badges screen, quest types (streak, transport variety, distance milestones) | Heavy | Done | Completed - 8 features
S9 | 2026-03-18 | Stats Screen | Stats & Visualisation screen (charts), trip statistics, CO2 numbers | Done | 🟢 Low | Completed - 3 features; gifted-charts removed (Metro bug); custom View-based bars
S10 | 2026-03-20 | Tech Debt + Optimization | useMemo (computeFavorites + recentPlaces), centralise+fix transport constants, fix floating promise, remove dead code, debounce OBB, more route prices | Medium | 🟢 Low | High
S11 | 2026-03-22 | Pre-Production | Email confirm, onboarding images, App Store metadata, QA | Done | 🔴 Asset dependency | Completed
S12 | 2026-03-25 | Launch / Buffer | Final regression, EAS build, submission, buffer for last-minute fixes | Done | 🟡 Medium | Completed
S11 | Mar 16 | 0 | 33 | 9 | Tech Debt
S12 | Mar 16 | 2 | 35 | 0 | Feature + Bug Fix

## 🏗️ Architecture
KlimaChallenge — Tech Stack & Architecture Reference
Quick reference for onboarding, handoff, or context refresh
TECHNOLOGY STACK
Layer | Technology | Version | Purpose | Key Files | Notes
Framework | React Native + Expo | SDK 54 | Cross-platform mobile (iOS/Android) | app/_layout.tsx, app.json | EAS build for production
Routing | Expo Router | v6 | File-based routing, pre-auth + tab flow | app/index, onboarding, login, register, (tabs)/user | Tab bar hidden; single tab screen
Language | TypeScript | ~5.x | Type safety across entire codebase | types/trip.ts, all .tsx files | Strict mode recommended
Persistence | AsyncStorage | ~2.x | Local trip + XP + settings storage | services/tripStorage.ts | Key: @travelapp_trips, userXP
Auth | Supabase | ^2.x | Email/password auth, session persistence | lib/supabase.ts | Project: vbjpigfbwvetsaoxpogd
Gestures | RNGH (react-native-gesture-handler) | ~2.28 | Favorites hold-to-add (LongPress) | user.tsx FavoriteCard | Required GestureHandlerRootView at root
Animation | react-native-reanimated | ~4.1.1 | XP bar, splash, XPToast, LevelUpOverlay, MainQuestOverlay | UserLevelCard, XPToast, LevelUpOverlay, MainQuestOverlay.tsx, index.tsx | useSharedValue + withTiming/Spring
Styling | NativeWind | CSS-based | Utility CSS on native | Various | Fallback: StyleSheet for complex layouts
Gradient | expo-linear-gradient | Latest | Login/register dark gradient overlay | login.tsx, register.tsx
Icons | @expo/vector-icons MaterialIcons | Latest | UI icons (modals MUST use MaterialIcons) | All modals, user screen | SF Symbols unreliable inside Modal on iOS
API | OeBB HAFAS (macistry proxy) | — | Station search, connection lookup, distance estimate | services/oebbApi.ts | Base: https://oebb.macistry.com/api — no ticket pricing returned
Charts | Custom View-based bars (no library) | — | Stats screen weekly bar chart, transport mix bars, progress bars | app/stats.tsx | react-native-gifted-charts tried S9 and removed (Metro bundler resolution bug); custom Views sufficient
KEY DESIGN DECISIONS & GOTCHAS
Decision | What was chosen | Why | Gotcha / Warning
Icons in Modals | MaterialIcons only | SF Symbols (IconSymbol) are unreliable inside React Native Modal on iOS — icons don't render | ⚠️ NEVER use IconSymbol in a Modal component
Gesture: Favorites | RNGH LongPress (native layer) | 5 other approaches failed: TouchableOpacity, Pressable, onTouchStart, PanResponder, scrollEnabled toggle all intercepted by ScrollView | Requires GestureHandlerRootView at app root
Colors | Palette from constants/Colors.ts | Design consistency: 3×3 custom palette (blue/green/red × light/mid/dark) | Never hardcode hex except #fff
Auth persistence | AsyncStorage session in Supabase | Standard Supabase RN setup; session survives app restart | Email confirmation DISABLED for dev — re-enable pre-prod
Trip date type | string after AsyncStorage round-trip | JSON.parse returns strings for Date fields; app treats as Date in multiple places | RESOLVED S9 — loadTrips() does date: new Date(trip.date) on parse. Tech debt closed.
OeBB distance | haversine × 1.25 detour factor | HAFAS API returns no distance; station lat/lng used with detour multiplier | Journey distance (from connection search) not captured — BUG
XP NaN guard | Seed from trips if stored='NaN' | Old installs stored the string 'NaN'; new parseInt guard re-seeds XP from all trips | XP stored as string in AsyncStorage; always use parseInt
SESSION LOG
Session | Date | Files Added | Key Architectural Decisions | AsyncStorage Keys Added | Notes
S1-S7 | 2026-03-14 to 15 | See Feature Registry | Trip CRUD, AsyncStorage, Supabase auth, RNGH gestures, Reanimated, TripRouteFields shared component | @travelapp_trips, @userXP, @klimaTicketCost, @travelapp_favorites | See Dashboard for full session history
S8 | 2026-03-15 | utils/questSystem.ts, utils/achievementSystem.ts, app/quests.tsx, components/ui/MainQuestOverlay.tsx | Quest rotation stored per-date/weekStart key in AsyncStorage; one-time main quest celebration flag; deep-linking via useLocalSearchParams | @questSelection_YYYY-MM-DD, @weeklySelection_YYYY-MM-DD, @quest_claimed_<id>, @mainQuestCelebrated, @mainQuestClaimed | 8 features; full gamification loop
S9 | 2026-03-16 | app/stats.tsx (new) | No chart library — custom View WeeklyBarChart to avoid Metro bundler issues; CO2 factor 0.16 kg/km (car 0.21 - PT 0.05); ISO week helper for 8-week window; TRANSPORT_COLOR map added in stats.tsx (inconsistency vs user.tsx TRANSPORT_ACCENT — tech debt #10) | None added | 3 features; stats screen complete
S11 | 2026-03-16 | constants/transport.ts, .claude/memory/ (project memory in git) | Canonical transport colors: Bus=blue.mid, Train=green.mid, Tram=red.light, Subway=green.dark. Memory files now version-controlled in .claude/memory/. | None added | Pure tech debt session. All 9 remaining debt items resolved.
S12 | 2026-03-16 | None (profile.tsx, user.tsx, stats.tsx modified) | RNGH gestures do NOT work inside RN Modal on mobile — use absolute-positioned View overlay instead. saveTrips([]) to clear trips (removeItem would trigger initialTrips fallback). useFocusEffect reloads trips+XP on every screen focus. | None added | 3 compounding bugs resolved in Delete All Trips feature. STORAGE_KEY=@travelapp_trips (not @trips). loadTrips() returns initialTrips when key missing.

## ✅ Feature Registry
KlimaChallenge — Complete Feature Registry
Every shipped feature with location and session
# | Feature | Category | Session | Primary Files | Description | XP Impact | Status
1 | Trip CRUD | Core | S1 | tripStorage.ts, user.tsx | Add, load, save trips to AsyncStorage | No | ✅
2 | 10 Dummy Trips (seed data) | Core | S1 | tripStorage.ts | Fallback initial data for fresh installs | Yes | ✅
3 | Financial Overview Card | UI | S1 | FinancialOverview.tsx | Collapsible savings card; klimaTicketCost €1400 baseline | No | ✅
4 | Transport Accent Bars | UI | S1 | user.tsx, user_styles.tsx | Color-coded left border on trip cards by transport type | No | ✅
5 | XP / Level System | Gamification | S2 | levelSystem.ts, user.tsx | getXPForTrip, calculateLevel, getLevelTitle, thresholds | Core | ✅
6 | UserLevelCard | UI | S2 | UserLevelCard.tsx | Animated XP progress bar with level title | Display | ✅
7 | Favorites (Hold-to-Add) | UX | S2 | user.tsx, user_styles.tsx | RNGH LongPress fill animation to re-add frequent trips | Yes | ✅
8 | Show All / Show Less Toggle | UI | S2 | user.tsx | Trip list defaults 5; expand/collapse all | No | ✅
9 | TripDetailModal (view+delete) | Feature | S3 | TripDetailModal.tsx | Tap trip to view details; delete with confirm overlay | Delete: subtract XP | ✅
10 | XP Seeding Fix | Bug Fix | S3 | user.tsx, tripStorage.ts | Seed XP from trips if stored value is NaN or missing | Fixes XP | ✅
11 | Logout | Auth | S3 | user.tsx, supabase.ts | Red-bordered button; signOut; routes to /onboarding | No | ✅
12 | Safe-Area + UX Overhaul | UX | S3 | user.tsx, user_styles.tsx | paddingTop:52, loading spinner, section icons, scroll padding | No | ✅
13 | Supabase Auth (signIn/Up) | Auth | S4 | supabase.ts, LoginForm, RegisterForm | Real email/password auth with session persistence | No | ✅
14 | Dark Login Screen | UI | S4 | login.tsx, LoginForm.tsx | ImageBackground + gradient overlay, Palette dark design | No | ✅
15 | Dark Register Screen | UI | S4 | register.tsx, RegisterForm.tsx | Matches login design; success state before redirect | No | ✅
16 | 3-Slide Onboarding | Onboarding | S4 | onboarding.tsx | Tappable dots pager; CTA only on last slide | No | ✅
17 | Animated Splash Screen | UX | S4 | index.tsx | Reanimated scale+fade 2s; session check before routing | No | ✅
18 | Trip Editing | Feature | S5 | TripDetailModal.tsx | mode:'view'¦'edit'; pre-filled form; transport/date pickers | XP delta | ✅
19 | XPToast | Gamification | S5 | XPToast.tsx | Floating '+XP' badge with spring+float animation on trip add | Display | ✅
20 | LevelUpOverlay | Gamification | S5 | LevelUpOverlay.tsx | Full-screen celebration overlay; spring-in; auto-dismiss 2.8s | Display | ✅
21 | Empty State | UX | S5 | user.tsx | Icon + message + CTA when no trips logged | No | ✅
22 | KlimaTicket Cost Setting | Settings | S5 | profile.tsx | Dropdown presets (€1400, €430, Custom); persisted | Affects savings calc | ✅
23 | User Profile Screen | Feature | S5 | profile.tsx | Avatar (initials), name, KlimaTicket picker; linked from header | No | ✅
24 | TripRouteFields (shared) | Refactor | S6 | TripRouteFields.tsx | Shared origin/dest/cost/distance component (light+dark theme) | No | ✅
25 | Price Autofill | UX | S6 | TripRouteFields.tsx | ROUTE_PRICES + TRANSPORT_FLAT_PRICES; fills cost on route change | No | ✅
26 | Suggestions Dropdown | UX | S6 | TripRouteFields.tsx | recentPlaces filtered as user types; sorted by frequency | No | ✅
27 | Swap Origin/Destination | UX | S6 | TripRouteFields.tsx | Swap icon button between input fields | No | ✅
28 | Distance Estimator | Feature | S6 | TripRouteFields.tsx, oebbApi.ts | Estimate button; haversine on ÖBB station coords × 1.25 | Affects XP | ✅
29 | OBB Distance Fix | Bug Fix | S7 | oebbApi.ts | searchConnections returns {journeys,fromStation,toStation}; summariseJourney uses haversine x1.25 when API returns 0m | Fixes 0 XP from connection trips | Done
30 | Price Autofill Mount Fix | Bug Fix | S7 | TripRouteFields.tsx | useRef(false) guard prevents autofill from firing on initial modal render - only triggers on user-driven field change | No | Done
31 | QuickAdd Dark Theme | UI | S7 | QuickAddTripModal.tsx | Full dark theme conversion - all inputs, pickers, connection list now match TripDetailModal edit style | No | Done
32 | Connection Description Autofill | UX | S7 | QuickAddTripModal.tsx | Selecting a connection auto-fills description field: "Origin -> Dest HH:MM TrainName" | No | Done
33 | Transport Type Default Empty | UX | S7 | QuickAddTripModal.tsx | Transport defaults to empty string; user must actively pick; dimmed placeholder; autofilled on connection select | No | Done
34 | QuickAdd Layout Improvements | UI | S7 | QuickAddTripModal.tsx | Distance moved below price; fieldLabels added; euro prefix + km suffix; 20% margin reduction; destination/origin gap reduced | No | Done
35 | KlimaChallenge PM Excel | PM | S7 | KlimaChallenge_PM.xlsx | 5-sheet project management file: Dashboard, Backlog & Tasks, Milestones, Architecture, Feature Registry | No | Done
36 | Quest System | Gamification | S8 | utils/questSystem.ts (new) | Daily pool (8), weekly pool (8), milestone quests (9); random 3/day rotation stored in AsyncStorage by date key; getClaimKey, timeUntilMidnight, daysUntilMonday helpers; MAIN_QUEST_ID + XP=2000 constants | Core (quest XP award) | ✅
37 | Achievement System | Gamification | S8 | utils/achievementSystem.ts (new) | 19 achievements across 5 categories (General, Distance, Transport, Streaks, Savings); computeStreak and computeSavedVsCar helper functions | No direct XP | ✅
38 | Quests & Achievements Screen | Feature | S8 | app/quests.tsx (new) | Segmented control (Quests ¦ Achievements tabs); loadOrRefreshSelection quest rotation; QuestCard, AchievementCard, SectionHeader components; section claim counts; XP award on claim (XPToast + LevelUpOverlay); deep-link via useLocalSearchParams tab param | XP on quest claim | ✅
39 | Main Quest Featured Card | Gamification | S8 | app/quests.tsx | MainQuestFeaturedCard at top of Quests tab; loads klimaTicketCost from AsyncStorage; red progress bar; euro stats (€X/€Y); CLAIM button awards 2000 XP; handleClaimMainQuest | 2000 XP one-time | ✅
40 | MainQuestOverlay | Gamification | S8 | components/ui/MainQuestOverlay.tsx (new) | Full-screen celebration overlay; 6 floating Reanimated stars; card springs in; trophy icon; stats row; progress bar; +2000 XP badge; one-time trigger via @mainQuestCelebrated AsyncStorage flag | Display | ✅
41 | Main Quest Break-Even Detection | Feature | S8 | app/(tabs)/user.tsx | checkMainQuest() called after every trip add; compares total savings to klimaTicketCost; shows MainQuestOverlay; onGoToClaim navigates to /quests | Triggers 2000 XP | ✅
42 | UserLevelCard Quests Link | UI | S8 | components/ui/UserLevelCard.tsx | Added onQuestsPress prop; Quests & Achievements row at bottom of level card with chevron; navigates to quests screen | No | ✅
43 | Profile View Achievements Button | UX | S8 | app/profile.tsx | View Achievements button in profile screen; deep-links to /quests?tab=achievements | No | ✅
44 | Stats & Insights Screen | Feature | S9 | app/stats.tsx (new) | 4 stat cards (trips, distance, CO2 saved, avg cost/trip); KlimaTicket progress bar (% + remaining); WeeklyBarChart (custom View, 8 ISO weeks, no library); Transport Mix (horizontal bars, %, color-coded); Top Routes (ranked list top 5); CO2 long-press tooltip; empty state; back button | No | ✅
45 | Stats Entry — FinancialOverview Donut | UI | S9 | components/ui/FinancialOverview.tsx | Added onStatsPress prop; SVG donut circle wrapped in TouchableOpacity; tapping navigates to /stats from main screen | No | ✅
46 | Stats Entry — Profile Button | UX | S9 | app/profile.tsx | Stats & Insights button in profile screen; navigates to /stats | No | ✅
47 | PM Updater Script | PM | S10 | pm_updater.py (new) | PMUpdater class with 14 methods covering all 5 Excel sheets. Dynamic row-finding (no hardcoded positions). Idempotent operations (skip if already exists). __main__ template block for Claude to fill at session end. Reduces per-session Excel update time from ~15min to ~2min. | No | Done